­

Progress Report
Community Plan 2022-2032
Quarter 4 2023-24 (April to March)

Summary - number of actions complete, green, amber, red and to be reported later under each Priority

Priority areas of action	Complete	Green	Status Amber	Red	To be reported later	Total
Putting learning at the centre	0	10	1	0	0	11
Our children and young people thrive	0	14	2	0	0	16
Thriving businesses and fair jobs	0	12	0	0	0	12
Caring, connected communities	0	12	3	0	0	15
Good quality, suitable housing for everyone	0	11	1	2	0	14
People live the healthiest lives possible	0	8	0	0	0	8
Total	0	67	7	2	0	76

       Key:

Statistical Measures
Project Measures

Putting learning at the centre / We will work with and support people of all ages to help them re-engage with education and learning or to improve their employability skills

Outcome: People experiencing barriers to employment are supported into sustainable work

				---BASELINE---		---LATEST---			---TARGETS---
Ref	Action	Measure	Comments	Status	Data	Period	Data	Period		Annual	Med / (3yr)	Long / (10yr)
A.1.1	Provide key worker based employability support and learning to targeted groups	Increase the percentage of employability participants progressing to positive destinations	A total of 1,513 individuals achieved a positive destination (56.8% of total engagements across all projects). / The 60% target has been identified as achievable, however, the Scottish Government No-One Left Behind (NOLB) approach to funding means that effectively only progression to employment or college learning can be counted as positive destinations as there are few training options outwith NOLB funding. This is likely to reduce the outcome rate and the target may be reviewed.	Amber	56.8%	2023-24	56.8%	2023-24		60%	62%	65%

Ref	Action	Measure	Comments	Status
A.1.2	Provide targeted support to adults facing barriers to employment	Number of people supported into training, education and employment	There have been 1,928 adults supported in the year with 530 progressing into employment and 601 accessing further and/or higher education. / Of the remaining adults, the Gateway to Employment programme delivered by Routes to Work South, has an increased focus on economically inactive adults and those with long term health conditions resulting in longer engagement and fewer job outcomes. / Target 2023-24 – 1,000 into employment/training/ education; and / Target 2024-25 – 1,200 into employment/education/ training.	Green
A.1.3	Provide a range of / employability programmes to parents through the Tackling Child Poverty funding programme	Number of parents/carers supported across the six priority groups into training, employment and education	335 parents have been supported across the six priority groups, 58 have progressed into work and 46 into training. / The Lanarkshire Employment Partnership (LEP) Tackling Child Poverty Group has developed and reviewed the Parents Employability Programmes to provide clear pathways across the three keyworker programmes – Supporting Families, Making it Work and Upskilling. / Target 2023-24 – 100 into training/employment/ education; and / Target 2023-24 – 100 into training/employment/ education.	Green
A.1.4	Provide specialist employability support to young people and adults with additional support needs	Number of young people and adults with Additional Support Needs supported into training, employment and education	44 young people and adults with Additional Support Needs have engaged in specialist programmes this year and two have progressed into employment. / 2023-24 – Programmes were reviewed with full delivery taking place from January 2024; and / 2024-25 – 30 progressing into training/employment/ education.	Green
A.1.5	We will work with and support people of all ages to help them re-engage with education and learning or to improve their employability skills’ – are you happy for me to add this again	Learners will be offered opportunities to learn skills that meet their needs across a range of settings. We will work with learners to:- / Enhance their parenting skills / Help parents to support their child’s learning	As a result of Community Learning and Development (CLD) work delivered by the Youth Family and Community Learning Service (YFCL) across a range of education and community settings the following has been achieved in 2023-24: / 590 learners have enhanced their parenting skills; and / 171 learners are better able to support their child’s curricular learning.	Green
		We will continue to support learners to progress to other appropriate learning opportunities, ensuring that we meet ongoing needs. We will work with learners to: / Help them re-engage with education/learning / Help them access volunteering opportunities / Help them access any other appropriate learning programmes or opportunities / Improve their employability skills	As a result of CLD work delivered by the YFCL Service across a range of education and community settings the following has been achieved in 2023-24: / 743 learners have re-engaged with education/ learning; / 243 learners are accessing volunteer opportunities across the service; / 593 learners have progressed to other appropriate learning programmes/opportunities; and / 735 learners have improved their employability skills.	Green

Putting learning at the centre / We will support young people to progress to further learning, work or training when they leave school

Outcome: Young people will be supported to progress to sustained positive destinations when they leave school

				---BASELINE---		---LATEST---			---TARGETS---
Ref	Action	Measure		Comments		Status	Data	Period	Data	Period		Annual	Med / (3yr)		Long / (10yr)
A.2.1	Support young people to progress to positive post-school destinations	Increase the School Leaver Destination Rate (SLDR) initial positive destination rate		The positive destination rate continues to increase and South Lanarkshire sits above the national rate of 95.9% and 6th highest of the 32 Local Authorities.		Green	96.2% / (SLC) / 95.5% / (Scotland)	2020-21	96.9% / (SLC) / 95.9% / (Scotland)	2022-23		97%	97%		97%
		Decrease the gap in the School Leaver Destination Rate (SLDR) initial positive destination rate		The gap between the positive destination rate for the most and least deprived 20% datazones has narrowed from 6.1% to 2.9% and reflects a rate of 95.5% for the most deprived compared to 98.4% for the least deprived. The national gap is 4.4%.		Green	6.1% / (SLC) / 4.4% / (Scotland)	2020-21	2.9% / (SLC) / 3.7% / (Scotland)	2022-23		2.9%	3%		3%
		Increase number and percentage of looked after school leavers in a positive initial and follow-up destination by local authority		There are 85 young people in this cohort classed as “care experienced”. The positive destination rate is 92.9% for this group of leavers, a slight increase from the previous year and is significantly higher than the national rate of 87.9%.		Green	SLC Initial 92.5% / Scotland / Initial / 86%	2020-21	SLC Initial 92.9% / Scotland / Initial / 87.9%	2022-23		93%	93.5%		94%

Ref	Action		Measure		Comments					Status
A.2.2	Deliver targeted support and learning opportunities to young people in the last 6 months of school through the Aspire programme		Number of young people engaged on the programme		The Aspire service has provided targeted keywork support to 503 young people in 2023-24. A range of employability programme provision was delivered including college-based vocational taster and employability group work.					Green
A.2.3	South Lanarkshire Council and Skills Development Scotland will work together to track the destinations of young people aged 16-19 including regular home visits		Number of young people who did not achieve/sustain a positive destination referred to support through tracking and re-engaged		The Employability Service tracked the initial destinations of all South Lanarkshire leavers and conducted a robust tracking exercise in collaboration with Skills Development Scotland to identify and engage young people who did not achieve/sustain a positive destination. In 2023-24, 91 young people were successfully re-engaged through this tracking exercise.					Green

Our Children and Young People Thrive / We will work to ensure children have the best start if life and become everything they can be

Outcome: Every family should get the right support at the right time for as long as they need

				---BASELINE--- ---LATEST---					---TARGETS---
Ref	Action	Measure		Comments				Status	Data	Period	Data	Period			Annual			Med (3yr)	Long / (10yr)
B.1.1	Four Family Support Hubs to promote a no wrong door approach and GIRFEC Pathways with community, third sector and universal pathways to be strengthened	By March 2025, there will be a 60% reduction in new referrals to Social Work Resources escalating to local office allocations		Social Work formally launched locality-based Family Support Hubs on 27 September 2022. The Family Support Hubs are community facing and accessible provisions based in Hamilton, East Kilbride, Lanark and Cambuslang localities. Families are the second largest referrer to the Family Support Hubs / In the past year, the Family Support Hubs have responded to 61% of the total referrals. This significantly decreases the volume of initial assessments being undertaken by Local Office Teams and will create more capacity within this part of the system to respond to child protection referrals. / Self-referrals are now the second largest referrers to the Hubs. Families are reporting improvements in family wellbeing.				Green	60%	2025	61%	2023-24			60%			TBC	TBC

Ref	Action		Measure			Comments					Status
B.1.2	Family Group Decision Making as a core partner to Early Years Multi Agency Service		By March 2024, 80% of families supported will report improvement in involvement in planning supports for their children and their family			Family Group Decision Making (FGDM) is offered to all pregnancy cases screened via EYMAS that are allocated for assessment and intervention. Additional support from peer support workers is also now available. This support can be offered to pregnant mothers and their partners when there are drug and/or alcohol issues present. / A parent’s plan process as an alternative to pre-birth CP has been tested in Hamilton Hub. This is now being scaled up across all 4 Hubs. / Outcome scales completed with families at the beginning and the end of their engagement in FGDM indicates a 100% improvement of all outcomes. This measurement scale is used with all families engaged in the support and data is available.					Green
			Implementation of a Parents Plan to prevent escalation to child protection			A parent’s plan process as an alternative to pre-birth CP has been tested in Hamilton Hub. This is now being scaled up across all 4 Hubs.					Green
B.1.3	Continue to refine and consolidate the Pathfinders approach		By March 2025, 60% of children and young people accessing Pathfinders will report improvement across three outcome indicators			The Pathfinders Programme is currently embedded within 7 schools in South Lanarkshire, with 14 Youth, Family and Community Learning Pathfinder Officer posts. Currently, Pathfinders are deployed in seven schools: Cathkin High; Trinity High; Stonelaw High; Lanark Grammar; Calderside Academy; St Andrew’s and St Bride’s, and Carluke High. This is funded through a mix of Whole Family Wellbeing Funding (WFWF) and Pupil Equity Funding. In 2023-24 the programme set a target to engage with 350 young people and families, providing support and sustained engagement that meets identified needs. In total at the end of March 2024, Pathfinders had worked with a total of 534 young people and families, which exceeds our target by 52.5%. / Pathfinder support is bespoke and provided through individual and group support. Home visits and parental engagement are key elements of the role. Pathfinder staff are well connected to key partners in the wider community to ensure appropriate referrals into and out of the provision. / The Pathfinders Team have successfully secured funding from the UNCRC Innovation Fund to develop a youth led consultation process that will allow young people to be the catalyst for change in relation to areas that effect their lives. This funding will support the further development of youth voice in relation to developing appropriate interventions and support and has enabled us to create rich opportunities for a committee of 21 young people participating in the programme to directly influence the service that they receive and be involved and influence decisions effecting them/the programme directly. / This element of the programme has three distinct phases:- / 1. Skills development – to allow the participants the opportunity to develop the key skills and knowledge to actively influence the programme and services they receive. / 2. Consultation- the participants will develop and deliver a / series of consultation events with their peer groups. / 3. Conference – young people involved will host a conference for key partners, sharing life experiences, barriers to participation and evidence of need to shape future policies. / Progress against measure: By March 2025, 60% of CYP accessing pathfinders will report improvement across three outcome indicators. / Impact is recorded through agreed fixed CLD impact measures that are reported directly through the South Lanarkshire CLD Plan. In addition, a range of Pathfinder specific progressive indicators have been developed to record participation levels and impact. / Target 5% increase in meaningful participation in school or learning in their social skills. Actual increase at year end 88%. / Target 5% increase in young people who recognise a positive adaptation in their behaviour, actual increase of 18%. / 5% increase in young people who identify positive development in their Health and Wellbeing 24%. / 5% increase in meaningful participation in school or learning. Actual increase of 12%.					Green
B.1.4	Test an improvement approach to support at least ten families with children with disabilities to cope with the financial demands of having a child/children with disabilities		By March 2025, 80% of families supported report an improvement in financial wellbeing and at least one of the other targeted outcomes / Improved health and wellbeing; / Reduced social isolation; and / Increased engagement with education, training or employment			Paths Away from Poverty is Funded by the Child Poverty Action Fund and aims to support at least ten families with disability through testing a bespoke support/navigator relationship with families where a child or young person has a disability and engages with parents and carers primarily. Referrals are primarily from Education (schools) and from NHS Lanarkshire to the third sector delivery partner – COVEY. / Outcomes and successes to date: / The project is supporting 5 families with a number of others in the referral pipeline. / Improved financial wellbeing (2 referrals for urgent financial wellbeing assessments). / Improved health and wellbeing (links strengthened with NHS colleagues, CAMHS, local GPs. Regular contact established with 3 families). / Reduced Social Isolation (3 families moving to weekly support; 1 young person referred for COVEY befriending support with other additional needs young people). / Increased engagement with education, training, or employment (no evidence at this stage). / The voice of families articulating what has changed for them because of the support they have received (families are choosing to engage and to receive support; personal plans being co-produced. More evidence pending as test evolves). / Evidence showing increase in benefits/entitlement (see above referrals for financial wellbeing assessments – too soon to evidence impact). / Increased participation in community activity (see reduced social isolation above).					Green
B.1.5	Four Family Support Hubs to promote a no wrong door approach and GIRFEC Pathways with community, third sector and universal pathways to be strengthened		By March 2026, 80% of parents supported will report improvements in family wellbeing			Social Work formally launched locality-based Family Support Hubs on 27 September 2022. The Family Support Hubs are community facing and accessible provisions based in Hamilton, East Kilbride, Lanark and Cambuslang localities. Families are the second largest referrer to the Family Support Hubs. / In the past year, the Family Support Hubs have responded to 61% of the total referrals. This significantly decreases the volume of initial assessments being undertaken by Local Office Teams and will create more capacity within this part of the system to respond to child protection referrals. / Self-referrals are now the second largest referrers to the Hubs. Families are reporting improvements in family wellbeing.					Green
B.1.6	Health and Social Work to work collaboratively with parents to identify strengths and areas for improvement in relation to neglect		Number of families completing the neglect toolkit by March 2025			103 Social Work staff have completed the Working with Neglect Toolkit training. Two more sessions are planned for 5 June and 2nd October 2024. A Practitioner Forum is now facilitated by the Child Protection Development Officer. Local offices and Family Support Hubs have introduced a reporting system to capture toolkit usage. Developments between Social Work and Health Visiting staff are being considered to scale up usage by introducing a targeted approach to toolkit usage and learning taken. / Consideration is being given to how to measure impact.					Green

Our Children and Young People Thrive / We will work to ensure that the health and wellbeing of children, young people and families is improved

Outcome: Every child and young person should be able to access local community services which support and improve their mental health and wellbeing

Ref	Action		Measure			Comments					Status
B.2.1	Deliver one Mellow Bumps Pregnancy Session in each locality in partnership with the Family Support Hubs		By March 2024, 80% of participants in the Mellow Bumps Pregnancy Sessions will report increased knowledge and understanding about stress, anxiety and self-care			The Mellow Bumps programme is part of the newly established parenting support group work pathway delivered from the Family Support Hubs (Lanark, Cambuslang, East Kilbride and Hamilton). The pathway has been introduced in stages in year 1 of the Hubs and is not fully operational with all programmes. One barrier to delivery has been trainer capacity. / As no Mellow Bumps programme has been delivered in full, collection and analysis of impact measure data will be a priority for the first half of year 2. / A Mellow Bumps programme was delivered from each of the four hubs in the first quarter of 2024/25 as planned. Attendance rates varied between hubs, groups tend to start with 6 expectant mums, with all hubs experiencing a level of drop out with the exception of East Kilbride. Of those mums that completed the programme feedback has been positive. The hubs plan to run the programme again after the summer and referrals are building again. / The groupwork pathway, including Mellow Bumps is reviewed regularly to ensure parenting support groups are targeted to meet presenting needs of those accessing the hubs and from info shared by partners.					Amber
B.2.2	Create and implement training at informed level to be delivered to Children’s Services staff through a Learn Online module		By March 2024, at least 50 Children’s Services staff will have accessed the Learn Online module and reported an increase in confidence in supporting children and young people at risk of self-harm and suicide			A Learn Online course has been created and shared through a variety of channels including the Education Sway, through NHS Lanarkshire Health Improvement links and as a precursor to in-person skilled level training. 89 South Lanarkshire Council employees have accessed the Lifelines Lanarkshire Learn Online module. Of those who accessed the training and provided feedback, all highlighted it as being helpful and/or informative.					Green
B.2.3	Key members of staff who support children and young people at risk of self-harm and suicide to attend Lifelines Lanarkshire training		By March 2024, at least 75% of staff who have attended Lifelines Lanarkshire training have shown an increase in confidence supporting children and young people at risk of self-harm and suicide following the training			Lifelines Lanarkshire skilled level training has been rolled out across services, attended by key members of staff in Education, Social Work, Health, and the Third Sector. Resources have now been adapted to enable delivery as a multi-agency training which has commenced. / 173 staff across South Lanarkshire Children’s Services have attended Lifelines Lanarkshire training. 92% of staff attending the training reported an increase in confidence supporting children and young people at risk of self-harm and suicide.					Green
B.2.4	Continue roll out of Kooth service and increase the use of this		By March 2024, at least 80% of registered users will report Kooth is effective in supporting them with their emotional wellbeing needs			An online digital support resource for young people called Kooth has continued to be rolled out across South Lanarkshire. Presentations have been given at a number of events such as the young person’s ‘Wellbeing Warrior’s Conference’ whole school assemblies and a session is planned for GPs. Between April 2023 - March 2024, 848 young people used the support. Over 90% of children and young people who responded, reported that they would recommend the service.					Green

Our Children and Young People Thrive / We will work to ensure that the life chances of children and young people in need of care and protection are improved

Outcome: Children and young people should grow up loved, safe, respected and listened to
Ref	Action	Measure	Comments	Status
B.3.1	In conjunction with care experienced young people develop ways that make it easier for them to participate in the ongoing improvement in key decision-making processes and capture the impact of their views and voices	70% of care experienced young people tell us that they feel more able to participate in key decision-making processes	Young people have had many more opportunities to influence change. The Champions Board was relaunched in January 2024 with new members uptake. The young people have been involved in the Keeping the Promise thematic sub-group and a forthcoming development session. In addition, they will be delivering and leading 2025 Care Day events. / Corporate Parents have agreed to be more visible. The Champions Board are putting a schedule of engagement in place including with the council’s Chief Executive. In addition, they are working closely with Housing officials, delivering a bespoke housing protocol for care experienced young people. Some young people are attending the Care and Prejudice Social Work event to showcase the work of the Champions Board. / 96% of young people visited within SLC units have been involved in the consultation, co-production and delivery of the suite of paperwork. This is reviewed via the Champions Board. The feedback has proved positive where young people fully included, with more opportunities for voice and participation as well as the paperwork being less cluttered with jargon and difficult language.	Green
B.3.2	Support young people from 16 years old to actively manage their Child Trust Fund and/or Junior ISA savings account currently administered by the Share Foundation	70% of young people report they are better informed about financial planning	All care experienced young people are supported to budget through advocacy support, the Promise Team and other corporate parents. This includes use of the Food Larder, Savings, Money Matters, and Welfare Support within the Care Hub. / The local authority has identified unclaimed ISA’s, and is working with Share Scotland to deliver the ‘Stepladder of Achievement for 15-17 year olds (these courses are about financial education). There are 18 registered for the programme. / £9,850 was shared amongst those completing courses. 4 completed all 6 courses, each gaining £1,500 for their Child Trust Fund. / 9 have gained between £150 and £1,100 for completing part of the course. / Contributions have also been made to care experienced young people’s Savings Accounts: (figures are only available for Junior ISA accounts*) e.g.: / £1,500 has been added to 1 account of a young person who has been adopted. / £2,430 has been added to 5 accounts of young people currently in care. / SLC has supported young people through the Winter Wishes initiative providing allowances over each of the last two years (£40k per year in total) over the Winter period to help with the cost of living challenges and in addition to set up allowance top ups for young people gaining their own tenancy. / All care experienced young people are supported to receive financial help in the form of education and budgeting. Money Matters meet with the Care Hub on a regular basis and offer drop-in sessions or bespoke contacts where appropriate. / Almost all young people supported with managing their finances report that they are better placed financially and more informed as a result of the support received.	Green
B.3.3	Meet housing needs through continued development of Person-Centred Pathway Planning	By March 2024, 100% of young people will have a Person-Centred Pathway Plan	Heads of Service meet fortnightly to review Care Experienced Young People (CEYP) on the Other Category Waiting List. Monitoring information has been developed jointly between Housing and Social Work Resources to reflect CEYP Application Status and prospects of housing. / Where a young person is identified as care experienced, they are added to the Other Category Waiting List where appropriate. / All CEYP to receive Person-Centred Pathway Planning to engage with Housing throughout their journey. A joint Housing and Social Work Pathway Planning Protocol was launched in January 2024. / As at 31 March 2024, 100% of CEYP on the ‘Other Category’ list had a Pathway Plan in place.	Green
B.3.4	Test the Throughcare Mental Health Pathway is offering the correct level of support for those with low and medium need	By March 2024, 75% of young people have been offered a low or medium need mental health support, report it has improved their mental wellbeing	Test concluded at the end of March 2024, with sustainable model being progressed through the School Nursing Team. 102 referrals were made between August 2022 - March 2024 (average 3.6 per month). Of these, 75% engaged with the service and 63% reported that the support has improved their mental wellbeing.	Amber
B.3.5	Provide targeted support to care experienced young people to engage and sustain participation in South Lanarkshire Local Employability Partnership (SLLEP) funded employability programmes	By March 2024, establish a baseline percentage of care experienced young people engaging with SLLEP funded employability activity progressing to a positive destination	57 care experienced young people participated in SLLEP funded employability programmes. 87.5% progressed to a positive destination of employment, learning (college etc) or further training. / The baseline going forward will be 65% progressing to a positive destination.	Green

Thriving businesses and fair jobs / We will work to make sure everyone has the same opportunities to learn new skills

 ----
Outcome: People experiencing barriers to employment are supported into sustainable work B -	=
				---BASELINE---		---LATEST---			---TARGETS---
Ref		Action	Measure		Comments		Status	Data	Period	Data	Period		Annual		Med / (3yr)	Long / (10yr)
C.1.1		Work with employers to progress people to employment	Number of employability participants progressing to employment		623 participants across all programmes have progressed into employment in 2023-24.		Green	623	2023-24	623	2023-24		625		650	700

	Ref	Action		Measure		Comments					Status
	C.1.2	Deliver sector-based training to employability participants		Number of people participating in sector based training		Sector Based Training via Routes to Work South (RTWS) – 42 participants undertook sector-based training and 13 progressed into employment. (Training undertaken included Site Health & Safety, CSCS, HGV Training, Forklift and SIA Security).					Green
	C.1.3	Provide in-work support and training through the Upskilling programme		Number of employed people engaging with the Upskilling programme		54 people engaged in the Upskilling Programme during April 2023 until March 2024. 6 participants completed training/qualification in areas of First Aid and Forklift Training. On completion, participants would have received a wage increase, job security and personal development. / During 2023-24 the Upskilling Programme was reviewed due to Scottish Government funding changes and now provides a blend of training and support to employed parents who require support to increase their hours/rate of pay or find alternative employment.					Green
	C.1.4	Work with employers to identify vacancies for progression for employability participants		Number of new employer engagement contacts developed and vacancies filled		A new Employer Engagement Team has been established to lead and co-ordinate employer engagement and support across the Employability Service, to identify work placements and suitable job progressions. Just over 300 employers have engaged, with approximately 315 vacancies filled.					Green

Thriving businesses and fair jobs / We will ensure that the place where you live is at the heart of our response to the climate emergency and help places to become sustainable

 ----
Outcome: Thriving town and neighbourhood centres provide a focal point for local communities B -	=
Ref	Action	Measure	Comments	Status
C.2.1	Complete the South Lanarkshire wide town centre visioning strategy which will give a strategic overview on the engagement and interventions with town centres over the next 10 years, and a series of town specific strategies and action plans will sit below this, giving a template for placemaking within our communities	Monitor and deliver town centre measures and initiatives in line with town strategies, Community Wealth Building and 20 Minute Neighbourhood approaches. / Town Centre Vacancy Rates – maintain at or below national averages / Businesses supported (including Social Enterprise) – support across towns and places	South Lanarkshire Council are working with key stakeholders across all our town centres to support businesses and invest in projects and initiatives which support the evolving way in which our towns are used by local communities. / In relation to vacancy rates, all our towns, except for East Kilbride, are maintaining levels at or slightly below the national average of around 14%. The council are seeking a move to more service-based businesses and more local traders, which is an encouraging trend and where possible are supported through Business Support. / Both East Kilbride and Hamilton contain shopping centres which have lost anchor tenants over the past year. East Kilbride has vacancy levels (c30%) well beyond the national levels and our own targets of circa 12%. Masterplan work to reduce retail space and increase leisure and housing provision is underway in both centres. / During 2023-24, there were 1,246 unique businesses supported, in key sectors, with the most prevalent sectors including: manufacturing, construction and engineering, and food and drink. This figure includes 509 start-up businesses, significant in bringing in new jobs and services to the South Lanarkshire economy.	Green

Thriving businesses and fair jobs / We will make it easy for businesses and social enterprises get all available help and advice from one place

 ----
Outcome: South Lanarkshire is an attractive place to start, grow and locate a business B -	=
				---BASELINE---		---LATEST---			---TARGETS---
Ref	Action	Measure	Comments	Status	Data	Period	Data	Period		Annual	Med / (3yr)	Long / (10yr)
C.3.1	Number of new South Lanarkshire business starts supported by Business Gateway / (Locally set target)	Total number of businesses/social enterprises supported / New start-ups	Over 2023-24, the council’s Business Support to new start-ups delivered under the Business Gateway (BG) brand supported 509 unique start-up businesses. From February 2024, and following an options appraisal, the BG contract was brought in-house in February 2024 and is managed and delivered by North Lanarkshire Council as lead for BG across the whole of Lanarkshire. South Lanarkshire Council has several satellite locations where BG staff operate from to ensure reach and accessibility to business/social enterprise across South Lanarkshire.	Green	500	2023-24	509	2023-24		500	N/A	N/A
C.3.2	Number of business support interventions per annum by Economic Development (grants, loans or advice) / (Locally set target)	Total number of businesses/social enterprises supported / Existing / organisations	The council’s wider support provided includes funding; dedicated (but not limited to) local business advisor support to assist businesses and plan for growth; access to expert help on a range of relevant topics including Finance; HR; Digital Development and Marketing. / 737 unique businesses/social enterprises were supported over the last 12 months. The council and partners also delivered 8 events with 982 attendees during this time across a range of activity e.g. Lanarkshire Business Excellence Awards, Build Lanarkshire and Women into Business etc. The council’s Business Team made 161 referrals to a range of council, partner and external business supports. This figure is lower than anticipated as it previously included ‘new start-ups’ performance results, which is now reported as a separate line.	Green	1,200	2023-24	737	2023-24		1,200	N/A	N/A
		Number and value of grants	South Lanarkshire Council’s Business Recovery and Growth Fund (BRGF) continues to provide larger grants targeted at existing Small and Medium sized Enterprises (SMEs) to support their strategic, longer-term sustainability and growth. This grant funds specific activities to help businesses/social enterprises adapt and grow via Capital Expenditure, Infrastructure Improvements, Training Support, Consultancy Support and Exhibition Support. / The council’s Micro Grant has had continued demand and success with available grants up to £3K match for businesses and social enterprises. Both grant sources are now funded under the new UK Shared Prosperity Fund. Over this reporting period 96 grants in total were awarded to the value of £674,273, this slight shortfall in spend is due to the transition over from European Regional Development Fund (ERDF) funding to UK Shared Prosperity funding on a short hiatus due to a change of funding criteria which required a systems update.	Green	£723,000 / (Made up of ERDF projected. / £483,000 / Plus / £180,000 SLC monies, plus / £60,000 UKSP)	2023-24	96 grants issued. / Value £674,273	2023-24		£723,000	N/A	N/A
		Grants awarded to businesses/social enterprises / Funding / leveraged	South Lanarkshire Council (SLC) grants are accessed through an online application form. For the council’s micro grant, a lighter touch application is operated, with a quick turnaround. There continues to be significant demand for both the SLC Micro Grant and Business Growth Funding and during this period the grants awarded levered in funding totaling £1,641,754. For every £1 of council grant spent, £2.43 of additional funding has been achieved.	Green	N/A	N/A	£1641.754	2023-24		N/A	N/A	N/A
		Total number of jobs / Jobs safeguarded	As a direct result of South Lanarkshire Council’s Business Support 490 FTE jobs have been safeguarded over 2023-24.	Green	500	2023-24	490	2023-24		500	N/A	N/A
		Total number of jobs / Jobs created	As a result of the direct Business Support on offer, South Lanarkshire Council is reporting 157 FTE jobs created across South Lanarkshire in this reporting period.	Green	Included in above baseline data figure as overall target -jobs created/ sustained	2023-24	157	2023-24		N/A	N/A	N/A
		Total number of jobs / Increase in / Turnover	As a direct result of South Lanarkshire Council’s Business Support interventions, South Lanarkshire Small and Medium Enterprises (SMEs) have increased turnover by £14,495,539 in 2023/24.	Green	N/A	N/A	£14.5m	2023-24		N/A	N/A	N/A

Caring, connected communities / We will continue to support and encourage every community to identify and act on their local priorities
Outcome: Communities feel empowered to identify and act on their local priorities

Ref	Action	Measure	Comments					Status
D.1.1	Ensure communities are engaged and supported to participate in local decision making	Develop standards and a framework for the planning, delivery and evaluation of place based Participatory Budgeting programmes	Participatory Budgeting (PB) ran in all Neighbourhood Planning areas in 2022/23, including Hamilton South to act as a method for the development of the new Neighbourhood Plan. / In 2024/25, the council’s Community Engagement Team will co-design a local evaluation model for place based PB which will also consider the approach, quality, outcomes and impact of this process. This will inform a framework and toolkit with local communities. They will also pilot more Third Sector delivery Place Based PB.					Green
		Strengthen the Neighbourhood Planning Participatory Budgeting approach by co-producing standards and a framework for the involvement of young people	Work is progressing on the Neighbourhood Planning Participatory Budgeting approach involving young people. Discussions are taking place on the implementation of the UNCRC right to voice and youth voice in the budget setting. / The NHS are carrying out internal work on implementing the UNCRC and a partnership working group on youth voice has been established. / An Engagement Partnership page has been established on the CPP website and a review of the South Lanarkshire Community Engagement and Participation Strategy will commence in autumn 2024. / Work is also progressing on involving young people in the Community Partnerships and to encourage the Community Partnerships to use the Lived Experience Fund to gather the views of youths.					Green
D.1.2	Fulfil statutory Locality Planning duties to reduce inequalities within identified priority neighbourhoods	Work with local communities in the areas of Hamilton South and East Kilbride South to identify local priorities and prepare a Neighbourhood Plan for their area	The Hamilton South Plan will be submitted to the Community Planning Partnership Board in September 2024 for noting. The stakeholders have written an action plan which highlights what improvements they would like to make between June 2024 and March 2026. / The East Kilbride Plan is still in development. Initial engagement has taken place and data analysis has highlighted hidden issues of inequality that have provided additional avenues of investigation. / Neighbourhood Planning community engagement in the East Kilbride South area has been carried out with the community views survey now being completed. Development of the Stakeholder Group is now a priority to build capacity.					Amber
		Evaluate the Neighbourhood Planning approach for South Lanarkshire and implement improvement actions	A review of the Neighbourhood Planning approach will take place in 2023/24.					Green
D.1.3	Ensure children’s rights and awareness of the United Nations Convention on the Rights of the Child (UNCRC) is embedded in the work of partner organisations	Develop a UNCRC webinar to support the understanding of children’s rights and the UNCRC across the CPP workforce	A group of young people are designing and delivering a filmed webinar for all public sector staff that provides information on the UNCRC and what public services need to do to ensure children’s rights are respected. This training will be available on the council’s online training platform and offered to all public sector organisations. This approach puts children and young people at the heart of preparations for the UNCRC (Incorporation) (Scotland) Act 2014 (Article 42 the right to know your rights).					Green

Caring, connected communities / We will bring communities together to share priorities and work jointly on them

Outcome: Communities feel connected, share priorities and work together to create change

Ref	Action	Measure	Comments	Status
D.2.1	We will bring communities together to share priorities and work jointly on them	Continue to develop and strengthen the membership of the Hamilton and East Kilbride Community Partnerships	Work continues to strengthen the membership of the Hamilton and East Kilbride community partnerships. / Governance arrangements including the Chair of the partnerships have still to be agreed.	Green
		Evaluate the Community Partnership approach with Cambuslang and Rutherglen and Clydesdale Community Partnerships and implement improvement actions	There are plans for a self-evaluation and review of future priorities, including group membership. This should be completed before December 2024. Processes for communication, monitoring, reporting and evaluation will also be developed. Data profiles will be developed for each locality. Training needs for the partnership volunteers are currently being identified, and a training plan will be devised and delivered.	Green
D.2.2	Young people will lead the way on actions to tackle climate change and nature loss	Support young people to continue to develop their leadership skills through engagement with the Community Planning Partnership Strategic Board on their Climate and Nature priorities	Following the success of an initial Development Session with the South Lanarkshire Community Planning Partnership Board and members of South Lanarkshire Youth Forum on Climate Change, Scottish Youth Parliament and South Lanarkshire Youth Council, a dedicated annual development session has been agreed to take forward to explore issues and present ideas to progress action to tackle climate and nature change. The Development Session supports the work and efforts of the wider forums and presents the opportunity to develop key skills and confidence of young people.	Green
		Increase youth voice and influence in Community Planning at a locality level through co-producing an approach to youth participation	Work has been undertaken between Youth, Family and Community Learning Service and Social Work to facilitate young people's participation in locality community planning through the youth participation network, that supports young people to actively explore and progress within the South Lanarkshire Youth Council and the Scottish Youth Parliament. This process will see young people supported to explore, identify and present issues and ideas at relevant boards and forums.	Green
D.2.3	Empower communities to improve their own health and wellbeing	Progress the implementation of the South Lanarkshire Age Friendly approach through the development of an implementation plan and supporting the Seniors Community to develop and deliver on actions	Seniors Together in conjunction with the council continue to deliver Age Friendly Older People Assemblies to engage with older people representatives of groups and clubs across South Lanarkshire to share plans to develop an Age Friendly South Lanarkshire. / The Leader of the Council provides an overview of the vision at each of these events. It is a requirement of the World Health Organisation’s (WHO) membership that there is commitment from the highest political person within the local authority. / An implementation plan has been developed and the WHO checklists for each of the eight age friendly domains will now be used as an engagement tool with older people to assist in identifying an age friendly standard for South Lanarkshire citizens. A precursor to this will be an engagement event on 5 September 2024, similar to an Older Peoples Assembly, with colleagues from the council’s Planning and Building Standards on the Local Development Plan 3. Some of the themes within the plan mirror the domains of an Age Friendly Community.	Green

Caring, connected communities / We will involve local representatives in community planning at all levels, including on the Community Planning Partnership Board

        Outcome: Community volunteers feel that they can effectively participate in and contribute to community planning at all levels
 People Thrive
Ref	Action	Measure	Comments	Status
D.3.1	Develop and deliver training/awareness raising activity to ensure that volunteers can participate effectively in Community Planning	Increase the number of volunteers in our Neighbourhood Planning Stakeholder Groups who feel confident about their role in Community Planning through capacity building, training and support	Building community capacity and increasing community participation continues to be a priority. Volunteering support and development work has commenced to build capacity and support and establish baselines for monitoring this progress. / A range of new engagement approaches are being used to ensure that residents are contributing on their own terms, in their own way and helping to bring the Neighbourhood Plans to life. Examples include the delivery of ACTIVATE which has catalysed the interest of local people, Let’s Talk About online discussion, the use of the community HUB model and “community conversations”. / Membership in Stakeholder Groups has increased or stayed the same. The council’s Community Engagement Team have yet to implement baseline reporting to monitor this. The East Kilbride Stakeholder Group requires further community development and input.	Amber
		Increase the number of volunteers in our established locality Community Partnerships who feel confident about their role in Community Planning through capacity building, training and support	Membership in the Clydesdale Community Partnership has increased by over 25% in the last year. There is now 43 volunteers with all Community Council areas having representation. There has been no change to the Cambuslang and Rutherglen membership levels. There are 17 volunteers and the partnership is currently reviewing membership and considering different methods of engaging the wider community. / The Partnership Community Development Officer is working with both Community Partnerships to complete a learning and development analysis to better understand their needs and to create a plan to deliver these activities. Enquiries are being made about the process for the Community Planning Partnership to obtain Volunteer Friendly status.	Green
		Train 12 employees/community representatives as Health in the Community (HIIC) Trainers and support them to achieve accreditation	The Scottish Community Development Centre (SCDC) hosted Health in the Community (HIIC) training on / 20 and 21 February 2024 where 12 trainers participated. This training is aimed at increasing community capacity, consolidating community development approaches to tackling inequalities in health. / This training highlighted the aims of the course; ideas and guiding principles; learning objectives and becoming a tutor. / The participants will require to carry out live sessions with various community groups across South Lanarkshire to achieve their accreditations.	Green
		Increase community representation on the Community Planning Partnership Strategic Board and provide youth voice opportunities	Three community members attend the Community Planning Partnership Board representing, Clydesdale and Cambuslang and Rutherglen Community Partnerships and Seniors Together. / The establishment of the Hamilton and East Kilbride Community Partnerships is progressing. Once the governance arrangements and future priorities have been confirmed, it is proposed that Chairs for each Community Partnership will be confirmed. / Young people are supported to explore, identify and present issues and ideas at relevant boards and forums including with the Community Planning Partnership Board and Community Planning Events.	Green
D.3.2	Upskill employees in participation and engagement approaches	Increase the number of employees who feel more confident in securing the participation and engagement of individuals and communities in their work	The Community Planning Partnership Learning and Development Plan Workstream Group have produced a final draft of eLearning materials and are meeting with the council’s Corporate Learning Team to arrange upload onto the Learn on Line platform.	Amber

Good quality, suitable housing for everyone / We will increase affordable housing supply and improve access to and choice of housing options that suit people’s needs
Outcome: Increase overall housing supply and improve access to, and choice of housing options, that suit people’s needs and are affordable
					---BASELINE---		---LATEST---			---TARGETS---
Ref	Action	Measure		Comments	Status		Data	Period	Data	Period		Annual	Med / (3yr)		Long / (10yr)
E.1.1	Deliver the council’s Home+ Programme	Increase the number of council homes in South Lanarkshire by 1,300		In total, 326 additional council homes have been delivered through the Affordable Housing Supply Programme since the council’s Executive Committee established the 1,300 target on 30 November 2022. This includes 104 new council properties and 222 purchased from the open market.	Green		0	2022	326	2022-24		TBC	1,300 (by March 2027)		TBC
		Maintain the percentage of tenants in council new build properties who are satisfied with their home		226 tenants within 11 new build housing sites were surveyed with a 39% response rate. While the overall satisfaction rate was 84%, in three sites 100% satisfaction was achieved.	Amber		91%	2022-23	84%	2023-24		91%	91%		91%
E.1.2	Provide settled accommodation to households experiencing homelessness	Achieve the annual Local Letting Plan target for social rented properties allocated to homeless households		The 2023-24 annual target for lets to the Urgent Housing Need list, comprising majority homeless households, has been achieved.	Green		55%-65%	2023-24	63%	2023-24		55-65%	TBC		TBC

Ref	Action		Measure			Comments					Status
E.1.3	Develop and implement the Strategic Housing Investment Plan (SHIP)		Annual approval of SHIP by Housing and Technical Resources Committee			The SHIP 2024-2029 was approved by the council’s Housing and Technical Resources Committee on / 8 November 2023.					Green
E.1.4	Develop and implement Local Letting Plans (LLP) with proposed annual targets		Annual approval of LLP targets by Housing and Technical Resources Committee			LLP 2024-25 targets were approved by the council’s Housing and Technical Resources Committee on / 7 February 2024.					Green

Good quality, suitable housing for everyone / We will work in partnership to improve housing quality and energy efficiency, whilst supporting a just transition to decarbonisation
Outcome: Improve housing quality and energy efficiency whilst supporting a just transition to decarbonisation
					---BASELINE---		---LATEST---			---TARGETS---
Ref	Action	Measure	Comments	Status	Data	Period	Data	Period		Annual	Med / (3yr)	Long / (10yr)
E.2.1	Improve overall energy efficiency of homes across South Lanarkshire	Increase the average Standard Assessment Procedure (SAP) score of all homes with an Energy Performance Certificate in South Lanarkshire	The SAP score has increased as a result of the installation of energy efficiency and decarbonisation measures.	Green	65.1	2021-22	67.0	2023-24		Increase by 1% from baseline	70	TBC
		Increase number of energy efficiency and decarbonisation measures installed across private homes in South Lanarkshire utilising national funding sources	In 2023-24, 161 privately owned properties benefitted from a total of 367 energy efficiency measures being installed through national funding sources.	Green	0	2022-23	367	2023-24		200	600	TBC
		Increase number of energy efficiency and decarbonisation measures installed in council homes in South Lanarkshire	The council continues to deliver its Housing Investment Programme to improve the energy efficiency of its properties and reduce energy costs for tenants. / Element 35 of the Scottish Housing Quality Standard (SHQS) based on EESSH1 criteria is the only energy measure currently being used, 95.39% of our stock pass the standard, which equates to 24,559 properties. / The council is awaiting guidance from the Scottish Government on the new Social Housing Net Zero Standard, expected to be published later in 2024-5 (it is likely that this measure will be revised following confirmation of new national net zero standard for social housing).	Green	0	2022-23	Data available June	2023-24		100 per year	TBC	TBC

Ref	Action	Measure	Comments	Status
E.2.2	Support the delivery of schemes to improve energy efficiency in homes across South Lanarkshire	Develop and implement the Energy Company Obligation (ECO) Scheme	The ECO scheme was launched in South Lanarkshire in July 2023. A total of 333 energy efficiency measures were installed in 127 properties during 2023/24.	Green
		Co-ordinate Energy Efficient Scotland: Area Based Scheme funding (EES:ABS)	During 2023/24, 45 properties (34 private, 11 council properties) were provided with external wall insulation with the aim of improving thermal efficiency and reducing the energy required to heat homes.	Green

Good quality, suitable housing for everyone / We will work in partnership to prevent and significantly reduce homelessness, and improve outcomes for those at risk of or who experience homelessness
Outcome: Prevent homelessness and improve outcomes for those at risk of or who experience homelessness
					---BASELINE---		---LATEST---			---TARGETS---
Ref	Action	Measure	Comments	Status	Data	Period	Data	Period		Annual	Med / (3yr)	Long / (10yr)
E.3.1	Deliver Housing Options Service with the aim of preventing homelessness	Increase the percentage of Housing Option interventions where homelessness is prevented	During 2023-24, 633 (60.8%) of homeless cases were prevented. The operating context in relation to the prevention of homelessness continues to be extremely challenging this year. The prevailing socio-economic conditions adversely impacted upon the ability to prevent homelessness during 2023-24. This trend has been mirrored nationally.	Red	73.5%	2021-22	60.8%	2023-24		70%	TBC	TBC
		Increase the percentage of former homeless households provided with a council tenancy that maintain their home for more than 12 months	Tenancy sustainment has remained strong this year and the target has been achieved.	Green	88%	2022-23	92%	2023-24		TBC	TBC	TBC
		Reduce repeat instances of homelessness	The performance is within the target. All repeat homelessness cases are reviewed to identify patterns and to inform future development and delivery of services.	Green	4.5%	2021-22	3%	2023-24		3%	TBC	TBC

Ref	Action	Measure	Comments	Status
E.3.2	Improve access to settled accommodation to homeless households	Continue to implement the Rapid Re-housing Transition Plan (RRTP)	Despite high levels of achievement against several key measures within the RRTP, the level of homelessness in South Lanarkshire continues to increase to unprecedented levels. This is noted in the RRTP annual review and mirrors trends across Scotland. A range of work is being progressed locally to help mitigate the situation and the Resource continues to engage with representative groups, such as the Convention of Scottish Local Authorities (COSLA) and Association of Local Authority Chief Housing Officers (ALACHO), to highlight the key issues which require to be addressed at a national level.	Red

People live the healthiest lives possible / We will ensure that all of our services work with people as early as possible to stop problems happening
Outcome: People are able to look after and improve their own health and wellbeing and live in good health for longer
					---BASELINE---			---LATEST---			---TARGETS---
Ref	Action	Measure		Comments	Status	Data		Period	Data	Period		Annual	Med / (3yr)		Long / (10yr)
F.1.1	We will continue to support people to improve their own health and wellbeing and exercise choice and control	Number of people participating in a co-produced Self Directed Support Assessment to exercise choice and control over their care		In Quarter 4, 1,014 co-produced assessments were approved, and 473 new co-produced assessments commenced. An increase in both measures is noted when compared to the Quarter 3, 2023-2024 position. To date, there has been a total of 3,459 co-produced assessments approved and 1,565 new co-produced assessments commenced exceeding the annual target of 3,000.	Green	2,984	2022/23		3,459	2023-24		3,000	3,100		3,200

Ref	Action		Measure		Comments					Status
F.1.2	We will continue to establish a Community Led Support approach to promote to promote positive health and wellbeing outcomes and community resilience		Number of employees trained in Community Led Support approach across all localities		Supported by Health Improvement staff, 362 Health and Social Care staff participated in Community Led Support (CLS) training.					Green
F.1.3	We will promote self – care and self-management including technology enabled care		Increase in the number of people supported by Technology Enabled Care to manage their own health and wellbeing		Lanarkshire’s Technology Enabled Care (TEC) Team continues to provide an integrated approach to sustaining people to live independently at home and within their community. It supports and facilitates hospital or integrated care discharges and may also be urgently requested as part of Adult Support and Protection planning or end of life care. The two main programmes of work include Telecare (South Lanarkshire only) and Telehealth (pan-Lanarkshire) such as the Connect Me remote health monitoring service, and Near Me video consultations. / Demand for assistive technology has continued to increase during 2023-24 with 13% of hospital discharge requests supported through the Home First pathway during March 2024, whilst 63% were installed to improve safety and reduce the risk of harm. / The transition of alert alarms from analogue to digital continues to make good progress with 227 digital alert alarms installed in March 2024, bringing the total number of installations to 6,580. A priority focus for the team is in terms of sustainability, where alarms are no longer required by service users. The target is to ensure the team is identifying 70 alarms per month that can be recycled and reused. To date, 965 digital alert alarms have been returned/uplifted and reused saving £156,330 on the cost of replacing these alarms.					Green

People live the healthiest lives possible / We will increase access, activities and supports that help improve mental health and addictions
Outcome: People, including those with disabilities or long-term conditions, or who are frail, are able to live, as far as reasonably practicable, independently and at home or in a homely setting in their community
					---BASELINE---		---LATEST---			---TARGETS---
Ref	Action	Measure	Comments	Status	Data	Period	Data	Period		Annual	Med / (3yr)	Long / (10yr)
F.2.1	We will continue to protect adults at risk from harm	Percentage of statutory supervising officer visits completed within timescale for local authority welfare guardianship orders	In Quarter 4, there was a total of 54 local authority welfare guardianship visits due with 94% (51) being completed on time. A decrease in this quarter is noted when compared with the Quarter 3, 2023-24 position of 98%, however, the target of 90% has still been achieved. To date, there was a total of 251 local authority guardianship visits due with 94% (237) being completed on time. This remains the same when compared to Quarter 3 2023-24.	Green	93%	2022/23	94%	2023-24		90%	90%	90%
		Percentage of statutory supervising officer visits completed within timescale for private welfare guardianship orders	In Quarter 4, there was a total of 499 private welfare guardianship visits due with 95% (474) being completed on time. An increase in this quarter is noted when compared with the Quarter 3 2023-24 position of 91%, target of 90% has been exceeded. To date, there was a total of 2,293 private guardianship visits due with 92% (2,108) being completed on time. This is an increase when compared to the Quarter 3, 2023-24 position of 91%.	Green	93%	2022-23	92%	2023-24		90%	90%	90%

Ref	Action	Measure	Comments	Status
F.2.2	We will continue to protect adults at risk from harm	Implement MAT standards across all localities	Medication Assisted Standards (MAT) are a set of nationally agreed evidence-based standards to enable the consistent delivery of safe, accessible, high quality drug treatments across Scotland. They were produced in response to the emergent public health crisis by the Drug Death Task Force. The standards are relevant to people and families accessing or in need of services and Health and Social Care staff responsible for the delivery of recovery orientated systems of care. There are a total of ten standards which services are working to fully implement. Progress on the implementation of the MAT standards continues across all localities with the focus for 2024 to ensure MAT standards 1 to 5 were implemented fully and embedded with the local service and this has been achieved with all five reporting a green rating.	Green

People live the healthiest lives possible / We will provide high quality day-to-day health and social care services that are accessible to everyone in our community who needs them
Outcome: Health and Social Care Services are centred on helping to maintain or improve the quality of life of people who use those services

Ref	Action	Measure	Comments	Status
F.3.1	Implement Discharge Without Delay to return people to their home or community safely	Embed Home First approach across localities to optimise independence of those discharged from hospital/prevention from hospital admission	The Care at Home Service has been augmented by the addition of four Home First teams based within each locality. The teams use a re-ablement approach, working with Allied Health Professional (AHP) colleagues to optimise independence of service users over a 6 week period and enable them to remain in their own homes, prevent hospital admission, or receive support immediately after discharge from hospital. During the fourth quarter of the year, those in receipt of Home First support required 44% less care at the end of their intervention. Performance has increased from 40% in Quarter three and continues to exceed the 25% target.	Green
F.3.2	We will support carers to maintain their caring role through a personal outcome approach	Number of new carers supported	1,398 new carers identified in South Lanarkshire; / 1,161 adult carer support plans progressed; and / 3,533 carers engaged and were supported.	Green