# Our Neighbourhood Plan for Hamilton South
## Annual Progress Report 2023-2024

If you need this information in another language or format, please contact us to discuss how we can best meet your needs.
Phone: 0303 123 1015 Email: equalities@southlanarkshire.gov.uk

## Introduction

Hamilton South is a ward with a population of around 22,000 people, that covers a number of areas, some of which are a priority for the Community Planning Partnership. Low Waters, Fairhill, Laighstonehall and Eddlewood are priority areas and subject to Neighbourhood Planning, which was started in summer 2023 with a local Stakeholder Group representing all areas, as well as staff from the NHS, South Lanarkshire Leisure and Culture and other partners. Since starting the Stakeholder Group has grown in number, with the biggest increase in representation coming from Eddlewood.Our Place Our Plan Hamilton South has set out its priorities using the previous plan created for Fairhill by widening its scope to cover all areas and beginning to identify clear outcomes that will benefit both the individual and collective communities.

Hamilton South has a number of community assets and some local groups who work with key organisations for the benefit of their community and beyond. The plans model will give all stakeholders the opportunity to widen networks, share resources and work together to influence and shape their communities from within.

### Schools within the area
There are six primary schools, some which have early years establishments attached, one other early year’s establishment and some privately run nurseries within Hamilton South. The area has one secondary school which has a catchment outwith the ward. Finally, there are two further primary schools on the area boundary which educates a small number of Hamilton South’s children.

- Hamilton Grammar School
- St John’s Primary School
- St Elizabeth’s Primary School
- Chatelherault Primary School and Nursery
- Woodside Primary School
- Our Lady and St Anne’s Primary School
- Woodhead Primary School and Nursery
- Hollandbush Nursery

Area population is around 22,252 people
Male 10,777
Female 11,475
Under 16 4,156
16 to 64 14,301
65+ 4,065
### Housing
Hamilton South has a mix of social, private, and privately rented properties. The social housing is mostly semi-detached houses or flat with gardens.
There are many new homes in the area, most of which are private homes, this means that Hamilton South is growing both in population and geographically.
Community assets Hamilton South has a number of assets which can be utilised by the local community, these include a Lifestyles Centre in Fairhill with a gym, library and community café, green spaces for recreation and sports, churches offering community activities and support, and many community groups and organisations providing a variety of activities and opportunities.

## History

The Hamilton South Neighbourhood Plan originally only covered Fairhill but was expanded to include Low Waters, Laighstonehall and Eddlewood. The Hamilton South Stakeholder Group was formed in July 2023 and has expanded in number, with groups and residents attending from all target areas.
The current plan is in draft form with a final one to be published later this year. The Community Engagement Team used the recent Participatory Budgeting exercise as an opportunity to explore the priorities further with local residents, and the general consensus was that the priorities are broad, so most identified actions could fit into one of them.
The Stakeholder Group are working to explore what can be achieved in the short, medium, and longer term under the plan’s priorities, and will create an action plan containing achievable and realistic goals for the area.
So far, the group have achieved coming together, deciding upon their priorities, and carrying out their first Participatory Budgeting exercise. The feedback from the stakeholders is that they still have a lot to learn and lots of work to do, but they are keen to learn from the experiences of others and use these to contribute to making Hamilton South a better place to live for everyone.

## Information on Participatory Budgeting

The first ever Hamilton South Participatory Budgeting exercise has taken place with money from The Big Lottery, the Community Planning Partnership and South Lanarkshire Council totalling £21,003.
The ideas stage of the process took place in December 2023 with 69 people telling us that they wanted to support families, children and young people, older people, and a community garden, amongst other things.
The Stakeholdler Group opted for grants of £3k per application with groups and organisations being able to apply more than once, if a different project was proposed. The stakeholders assessed and approved the applications and local people voted via doorstep dialogue, online and during community pop up events.

1. Nine proposals were received.
2. 411 people voted, totalling 1,226 votes.
3. All proposals full or part funded.
### The following projects were funded:
1. Eddlewood Activity Group
2. Low Waters Lot Community Group – community growing project
3. Hamilton Guides
4. Low Waters Lot Community Group – dead hedge project
5. Eddlewood Football Association
6. Hamilton South Church
7. Hamilton Brownies
8. Low Waters Community Group
9. St Elizabeth’s Primary School

Some of the local activists are to be applauded for stepping up to help the Community Engagement Team get to as many residents as possible. The groups who received money are now focusing on their own priorities, whilst supporting the wider goal of a ward wide plan for Hamilton South.
All projects have set outcomes and are subject to evaluation once the activities are fully delivered. The Stakeholder Group voted to carry out an audit process also, so randomly selected groups will take part in this process in late 2024.
## Priority Progress that has been achieved

Priority	Topic	Actions
1	Physical environment	Low Waters Lot Community Group have worked alongside the councils Grounds Department to clean up the area they wish to manage in the future. / Eddlewood Football Association have applied to manage Eddlewood Park under Community Asset Transfer.
2	More leisure and social opportunities	Eddlewood Activity Group are running school holiday programmes for families in partnership with Hamilton South Parish Church. / Hamilton South Parish Church run a weekly community lunch and reuse shop for all members of the community. / Hamilton Universal Connections runs a variety of activities for both adults and young people.
3	Greater community safety	Scottish Fire and Rescue have joined the Hamilton South Stakeholder Group, allowing for better communication and links to local people.
4	Easier to get about/moving around	his priority will be actioned in the coming year.
5	More variety of shops/businesses	Community Action Fairhill started a weekly community food stall in Fairhill Lifestyles Centre.
6	Housing improvements	This priority will be actioned in the coming year.
7	Stronger and better communities	This priority will be actioned in the coming year.
8	Better financial wellbeing	Community Action Fairhill started a weekly community food stall in Fairhill Lifestyles Centre. / 60 local people benefitted from free sanitary provision.
9	Health improvements	Fairhill Lifestyles facilitates the Weigh to Go programme in partnership with NHS Lanarkshire every Friday. / The Health Improvement Team are active stakeholders in the Hamilton South Stakeholder Group.
10	Better education, training and employment opportunities	Hamilton Universal Connections support local adults to improve their reading, writing and number skills.

## Development Plans

The main actions for the next year are to finalise the plan with clear priorities and share with the Community Planning Partnership. In addition, an action plan will be created with short, medium, and longer terms goals which are realistic, achievable and involve as many stakeholders as possible. The Stakeholder Group are planning a workshop in May/June 2024 to start the process of creating an action plan.
The individual groups have plans to meet or get closer to their goals too, these include becoming a Scottish Charitable Incorporate Organisation (SCIO), taking over land through the Community Asset Transfer process, tapping into training to build skills and knowledge and to take forward the projects that they received Participatory Budgeting money to carry out.
Finally, some of the Stakeholder Group members have signed up to the Activate course. Activate is flexible learning programme designed by the University of Glasgow and delivered in communities throughout Scotland. Activate attracts local community activists, volunteers and others who want to make a difference in their communities and learn more about the values and principles of community development.

## Actions for 2024-2025
Physical environment
  - Better use of green spaces.
More leisure and social opportunities
  - Support the development of the Low Waters Hall and Community Group.
Greater community safety
  - More awareness of what goes on in the community.
Easier to get about/moving around
  - Improved paths and walkways.
More variety of shops/businesses
  - Forge links with local businesses, so they can support the community.
Housing improvements
  - Build relationships with South Lanarkshire Council (SLC) Housing and other providers.
Stronger and better communities
  - Provide opportunities for local people to connect and come together.
Better financial well being
  - Provide low cost and free activities/services for community members.
Health improvements
  - Improve wellbeing through reduction in social isolation and increased community participation.
Better education, training, and employment opportunities
  - Provide educational based opportunities that support skills development.

## Case Study
We are a group of Hamilton residents who are passionate about promoting everything to do with community growing, biodiversity and sustainability. Our committee, known as “Low Waters Lot Community Group”, aims to care for the site of Hutchison Street Park locally known as “Hutchy Park”. We are working alongside the Community Engagement Team to secure a lease through Community Asset Transfer so we can fully develop the site into a community garden. Our future is to create a safe space in Hutchison Street Park for all the surrounding community to enjoy.
The Community Engagement Team have also supported us to receive two amounts of Participatory Budgeting funding. The funding will firstly invite the people of Hamilton South to grow food and flowers in their own house and/or garden. We will begin with sunflowers and potatoes which will be part of a competition where prizes will be given out to competitors. This will give us an opportunity to network with the local community and chat about what we are planning for the future and encourage them to become involved in the community garden.
Secondly, we will purchase garden tools, plants, and equipment to develop a community greenspace area on Hutchison Street, Low Waters. We will also secure the boundary by building a dead hedge to promote wildlife such as butterflies and birds. We are really looking forward to creating the hedge on the south of the park and having other groups within the community involved. We are delighted to have gained PB funding as it will not only secure the boundary and benefit nature but will enhance the community aesthetically pleasing to visitors who visit the garden. Low Waters Lot Community Group

## Quote
We create a safe space where young people grow in self-confidence, make new
friends, and acquire skills to be proud of.
The children and young people develop resilience and understand the importance of a growth mindset.
We are also delighted to receive a funding grant from the South Lanarkshire Council Participatory Budgeting process. We are very thrilled to be able to provide new supplies to the girls, replace some of our old equipment and support families with their annual Girl Guiding census payment. 10th Hamilton Brownies

## Contact
If you would like to find out more or to get involved please contact:
Community Engagement Team
0303 123 1017
communities@southlanarkshire.gov.uk