# Development Plan Scheme and Participation Statement 2024-5

If you need this information in another language or format, please contact us to discuss how we can best meet your needs. Phone 0303 123 1015 or email equalities@southlanarkshire.gov.uk

## What is the Development Plan Scheme?

A Development Plan Scheme (DPS) is prepared and updated by South Lanarkshire Council (the council) every year. For 2024, the DPS provides further detail on our engagement strategy and evidence gathering in preparation of our next Local Development Plan. This work will inform how our places look in the future, where new houses and places of work will be built, how services and facilities such as schools and travel will be provided and identify the places and buildings to be protected.

DPS 2024-5 includes the projected timetable for delivery of the different stages of the plan making process, as well as the Participation Statement which explains how and when we will ask stakeholders including local communities and key agencies to become involved.

## What is the Development Plan for SLC?

Development plans are important as they define how we use our land and what areas requires greater protection. It also provides policy which guides decisions on applications for planning permission. The current arrangements that apply across Scotland are shown in the diagram below.

Scottish Government's policies and proposals for the development and use of land. Incorporates any adopted regional spatial strategy (RSS) when preparing, revising or amending the NPF.

A planning authority, or authorities acting jointly, prepare long-term spatial strategies for the strategic development of an area. RSS are not part of the statutory development plan but have an important role informing future versions of the NPF and LDPs (Local Development Plan).

councils must prepare one or more LDP for their area. It shows how local places will evolve in the future, including where development should and should not happen. It must take into account the National Planning Framework and any registered local place plan/s (LPPs) for the area the LDP covers. It should also have regard to any RSS and the Community Plan for the area it covers.

LPPs are community-led plans prepared by community bodies setting out proposals for the development and use of land in their local area. It must have regard to the NPF, any LDP which covers the same area, and also any neighbourhood plan which covers the same area. LPPs are not part of the statutory development plan but have an important role to play in informing LDPs.

National Planning Framework 4 was published and adopted by the Scottish Government on 13 February 2023. It sets out 33 national planning policies which represent the Scottish Government’s long term spatial strategy for Scotland. These policies are used to assess planning applications and provide the direction for what the council’s Local Development Plan should include.

The table in Annex 1 shows how these policies link to other national and the council’s own strategies and policies.

South Lanarkshire Local Development Plan 2 was adopted in April 2021 and represents the council’s spatial policy for its area. It includes sites that are allocated for development as well as detailed policies on matters such as climate change, the green belt and rural area, housing, town centres and transport.

It is accompanied by other documents including Supporting Planning Guidance covering Developer Contributions, Renewable Energy, Electric Vehicle Charging Infrastructure and Development at a Dwellinghouse.

Regional Spatial Strategies will look at strategic development issues – in the case of South Lanarkshire across the Glasgow City Region. There several working groups associated with this joint approach that have met in early 2024 to explore what issues need to be addressed regionally. This will be developed in tandem with LDPs.

Local Place Plans are a new opportunity for local communities to get involved in the planning system by setting out proposals for the development and use of land in their area. Once it has been registered by the planning authority, we have a legal responsibility to take them into account in the preparation of the next Local Development Plan. We have now issued an invitation to communities to prepare Local Place Plans and have an online register of interest on our website: Local Place Plans. For further information, you can refer to the circular Planning circular 1/2022: Local Place Plans.

## The next Local Development Plan for SLC

The council formally agreed the preparation of the next Local Development Plan (to be known as LDP3) in summer 2023. Early engagement and evidence gathering are now underway to prepare an Evidence Report, based on the requirements published by the Scottish Government in May 2023: Local Development Planning guidance. The evidence will include information and data and qualitative as well as the ‘lived experience’ of everyone active in the council area. By doing this will capture the aims and ambitions of the council and its partners, stakeholders and communities. Annex 2 provides further details. There are some other key assessments that need to be developed alongside the LDP, which help to inform decisions and ensure that the plan meets other legislation requirements. A list of these is provided in Annex 3.

Once complete the Evidence Report is submitted to Scottish Ministers for a Gate Check. This to allow an assessment by an independent Reporter of whether the evidence we have produced is sufficient to let us start preparing the Local Development Plan. It will also check that that we have carried out appropriate engagement and consultation.

When we receive confirmation that the Gate Check is complete work, we will start on the Proposed Plan. This will be map based with site briefs and masterplans to detail how sites will be developed. Sites must be deliverable and free from constraints, and we will be actively engaging with developers and key agencies to evidence this. Undeveloped sites in LDP2 will be looked at again and may be removed if they are no longer deliverable or viable or accord with the policy direction in NPF4.

A Call for Ideas will be carried out early on in this stage of plan preparation so that propose ideas for any part of the plan can be submitted, including policy or suggestions for development sites.

Once the proposed plan has been prepared, we will carry out formal consultation of a minimum period of 12 weeks. This will include neighbour notification for anyone who owns, or leases sites or neighbouring land affected. During this period anyone can make representations to the council either in support of the plan or if they wish to object.

After the consultation period we can modify the proposed plan to take account of representations made to the council or consultation responses from key agencies.

When we cannot agree modifications then the representation is considered unresolved. When this happens, the proposed plan is submitted to Scottish Ministers for examination carried out by a reporter from the Department for Planning and Environmental Appeals. Once the Examination is complete the Reporter will prepare a report setting out their recommendations and any modifications they require to be made. The report will be submitted to the council along with anyone who has made unresolved representations. The council are to make the modifications except in limited circumstances. After this we will carry out the process for the formal adoption of the Plan.
## The Timetable

Key stages	Timetable	Actions
Evidence gathering	Summer 2023- Autumn 2024	Includes: Local Place Plan register, Self-build register, Urban Capacity Study, Green Belt Review, Settlement Boundary Review, Open Space Audit, Play Sufficiency Assessment, Retail Studies, Town Centre appraisals, Vacant and Derelict Land Survey, Housing Land Audit, Employment Land Audit, Conservation Area Appraisals, Dismantled Railways Mapping.
Development Plan Scheme and Participation Statement update	May 2024	We published an approved Participation Statement in late 2023. This has been updated to reflect the current engagement strategy and timetable for participation throughout 2024/25.
LDP3 early engagement	Summer 2023 – Winter 2024	Comprehensive early sense check on evidence gathering to identify areas of conflict or disagreement in terms of data interpretation. Engagement requires capturing hard to reach, young people, minority groups and place-based communities to ensure we capture the lived experience.
Preparation of Evidence Report	Winter 2024/25	The evidence report will identify any gaps in the evidence required; our interpretation of the evidence gathered and the implications for the proposed plan; and a summary of any conflicting views on the evidence and lived experience. Approval of Full council required prior to submission for the Gatecheck.
Scottish Government Gate Check	Spring 2025	Submission of evidence report to Scottish Government who will appoint a Reporter to identify any unresolved issues and provide evidence base for developing strategy is robust.
Strategy development for Proposed LDP3	Winter 2024 – Spring 2026	Development of key strategies to support development of LDP, including Open Space Strategy, Housing Needs and Demand Assessment and Employment Land review.
Development Plan Scheme and Participation Statement update	May 2025	Updated to provide engagement strategy for developing Proposed Plan.
Call for ideas and continuing engagement	Spring 2025	The call for ideas will be an invitation open to everyone to propose ideas for any aspect of the new local development plan including local policy/guidance and land allocations.
Development Plan Scheme and Participation Statement update	May 2026	Updated to provide stakeholder consultation timings and process.
Proposed Plan consultation	Spring 2026	Proposed Plan presented to Full council for approval. / One approved statutory consultation of minimum 12 weeks to allow any representations from stakeholders, including the public, which seek to make changes to the plan. This stage will include targeted engagement with key stakeholders and communities most affected by the proposals.
Modification of the Proposed Local Development Plan	Autumn 2026	Modifications carried out to proposed plan. The Regulations state that there is no requirement to invite comment on the Modification Report. However, this depends on whether new information has been submitted that challenges the evidence position in terms of strategy development. / Approval of Full council required for any modifications.
Development Plan Scheme and Participation Statement update	May 2027	Updated to provide Participation Statement as part of LDP Examination submission.
Examination	Winter 2026	Council submits Proposed LDP to Scottish Government for examination of any unresolved issues. DPEA issues Examination Report providing council with recommendations on how to resolve these issues.
Adoption	Winter 2027	Modifications and any new material considerations incorporated into Proposed LDP and presented to council for adoption.
Post-Adoption Monitoring and Delivery Programme	2028 onwards	Monitoring and delivery programme for LDP established and updated regularly to identify any modifications or requirements to ensure delivery.

## Participation Statement

To develop the Local Development Plan (LDP3), we are asking you to share with us your thoughts and ideas of how to create successful and enjoyable places within South Lanarkshire. Our Participation Statement outlines the range of engagement we will be carrying out and who we will interact with. We aim to engage with as many people as possible to collect the information needed to reflect the strengths and opportunities that we can build upon. If it’s done right, LPD3 will embody everything we’ve learned from you and will provide local approaches to meet these identified needs.

We would like to hear from you, and in your own words, about the things that matter to you. As part of this, we recognise you may have many different roles and interests. We believe that everyone has the right and the skillset to get involved, and by doing so you will be making a valuable contribution to the improvement and wellbeing of your area. This is your plan, and it needs to embody your views and the diverse needs of communities within South Lanarkshire. To reflect our diverse needs, we will prepare individual programmes to connect with communities. Targeted strategies to reach underrepresented groups are included in this. A more detailed Engagement strategy is provided in Annex 4.

The Participation Statement is a ‘living’ document that will regularly be updated to reflect good practice and changing circumstances. We will listen to feedback from your experience of engagement with us and we will take steps to make improvements going forward. We hope our Participation Statement helps you to feel empowered, welcomed, and that your input and lived experience of South Lanarkshire is hugely valuable to us.

What general principles will we follow?
- The approach to engagement on LDP3 will be shaped by the principles highlighted in the National Standards for Community Engagement.
- We will ensure that people with protected characteristics (including race, age, gender, sex, sexual orientation and disability) are not discriminated against, and are actively included in the engagement process.
- The contents of the draft Effective community engagement in local development planning guidance: consultation published on 24 May 2023 will be used to shape our engagement activities with local communities.
- We will also incorporate the Planning and Building Standards Consultation Communication and Engagement Strategy 2021 into our engagement methods.
Our inclusive approach
- We will encourage participation from as wide a range of stakeholders as possible throughout the LDP process. We want to make it as easy as possible for everyone with an interest to engage in its preparation.
- Information will be provided in accessible formats to meet the needs of our varied stakeholders. We will exchange and gather information using graphics and audio to remove the barrier for those with vision impairment or literacy and numeracy challenges. We understand that using technology won’t always be the best method for everyone, and in these cases we will use alternative methods. In addition to English, we will provide the document in additional language formats.
- Engagement with children and young people, older people, disabled people and Gypsy/Travellers is a statutory requirement. We will work with the council’s Education Service as well as organisations such as the Youth Panel, Seniors Together, the Access Panel, Lanarkshire Ethnic Minorities Action Group and Minority Ethnic Carers of People Project to develop appropriate methods to engage.
- We will develop a programme with Voluntary Action South Lanarkshire to facilitate engagement with the many local voluntary groups across the council’s area.

How will we publicise engagement opportunities and provide feedback?
We propose to use:
- The creation of an online information hub
- Email and letter mailings
- Adverts in local newspapers and South Lanarkshire View
- Documents held at local libraries
- South Lanarkshire council website
- The generation of a regular newsletter
- Social media
- Collaboration with Community Planning colleagues
- Posters and flyers
- For underrepresented groups we will use representative organisations to reach a wider audience

An emphasis on good communication
- We will identify the method of engagement by asking those we want to hear from. For large groups we may focus on the method that is most preferred.
- An interactive online hub will be created to enable updates on the plan making process to be provided as well as to invite comments and suggestions.
- We will use the relationships that already exist within communities, in particular where there has already been extensive SLC engagement to produce Neighbourhood Plans.
- We won’t over consult, and we may focus on topics or issues that people are most interested in.
- Where it would be advantageous to the stakeholder, we will facilitate other services to provide questionnaires and the Place Standard Tool on our behalf.
- We will participate in other consultations being carried out by the council and its partners.
- We will request invites to attend events within communities and work closely with colleagues in Community Planning who have already established strong links to communities.
- We will ensure that the format of communication is led by accessibility and ease of use.
- We want to involve communities who may be excluded from participating due to disadvantage relating to social or economic factors.

Ways in which we will gather information and comments include:
- A newsletter to share updates on the process and the outcomes from engagement.
- Using the Place Standard Tool, including a simplified version for children and young people.
- Holding Exhibitions and workshops.
- Use of the council’s Citizens Panel and Peoples Panel.
- Online surveys and keypad voting and standpoint terminals.
- Work closely with our Community Planning Partnership partners to engage with people living in communities experiencing socio-economic difficulties to gain a better understanding of their place.
- We will promote and facilitate the participation of children and young people under the age of 25 to seek views on their lived experience. Proposed methods of engagement will include the Place Standard Toolkits to support conversations between educators/teachers and children, and capture views about play needs and opportunities in their area, including likes and dislikes about their places. We will engage through South Lanarkshire Youth council, Youth Parliament Representatives, student representatives in higher education and the council's Education Services.
- We will seek the views of and engage with Gypsies and Travellers to help gain a perspective on their distinct planning needs. Positive engagement with Gypsies and Travelling People will be facilitated through dialogue with representative organisations and the council’s Gypsy/Traveller Liaison Officer. Attention will also be given to non-written and face-to-face on-site engagement.
- We will work with groups and organisations representing disabled people and older people to establish the most suitable methods of engagement and multimedia formats to share and collect information.

Who can participate?
Participation in the preparation of Local Development Plan 3 is open to everyone and inclusion will be encouraged, including (this is not an exhaustive list):
- South Lanarkshire residents and those with an interest in the area
- Landowners, developers and housing providers
- Business, industry, and tourism groups
- Elected members
- Underrepresented and minority groups
- Religious bodies and organisations
- Voluntary organisations
- Neighbouring authorities
- Rural communities

Other key groups:
- Children and young people
- Disabled people
- Gypsies and Travellers, and Showpeople
- Community councils
- Older people
- Communities experiencing socio-economic disadvantage
- Community bodies who have expressed an interest in, or have completed, a Local Place Plan

Key Agencies:
The key agencies are set out in the Town and Country Planning (Development Planning) (Scotland) Regulations 2023 as follows:
- NatureScot
- Scottish Environment Protection Agency (SEPA)
- Scottish Water
- Scottish Enterprise
- Strathclyde Partnership for Transport (SPT)
- NHS Lanarkshire
- Historic Environment Scotland (HES)
National and Regional agencies:
- Transport Scotland
- Scottish Forestry
- Sport Scotland
- Architecture and Design Scotland
- Central Scotland Green Network Partnership
A sample of topic interest groups:
- Natural Environment and Climate
- Historic Environment
- Art, Leisure and Culture
- Active travel and transport
- Town centre and business groups
- Food growing and local living

## Mediation

The use of mediation to help build bridges between stakeholders and explore, reduce or resolve issues of dispute in development planning is highlighted in the Scottish Government - Circular 2/2021: Guidance on the promotion and use of mediation in the Scottish Planning System LINK Mediation has the potential benefits of opening up communication, improving relationships and encouraging a way to move forward from disputes, however this does not guarantee dispute resolution or an agreement between parties.

It is a voluntary process and be facilitated either by an impartial third party or through ‘informal mediation’ where planners and other relevant stakeholders take a mediation-style / faciliatory approach in their work. We will have regard to any requests for the use of mediation through the consultation process of the Participation Statement. Where the council has been requested to enter into mediation during the local development plan process, each case will be considered on its individual merits.

## Annex 1 Sustainable places
NPF4 Policies	Key Scottish Government links	Council Plans/Strategies
Tackling the climate and nature crises / Climate mitigation and adaptation / Biodiversity / Natural places / Soils / Forestry, woodland and trees / Historic assets and places / Green belts / Brownfield land, vacant and derelict land and empty buildings / Coastal development / Energy / Zero waste / Sustainable transport	Land Use – getting the best from our land: strategy 2021 – 2026 / Making things last: a circular economy strategy for Scotland / Scotland’s Energy Strategy / Scotland’s Environment Strategy / Scotland’s Forestry Strategy / Scottish Biodiversity Strategy	Council Plan – Connect / Community Plan / Various neighbourhood plans / Sustainable Development and Climate Change Strategy / Carbon Management Plan / Local Heat and Energy Efficiency Strategy (under preparation) / Biodiversity Strategy / Glasgow and Clyde Valley Forestry and Woodland Strategy / Local Transport Strategy (under review) / Park and Ride Strategy / Various active travel studies

Liveable Places
NPF4 Policies	Key Scottish Government links	Council Plans/Strategies
14. Design, quality and place / 15. Local living and 20-minute neighbourhoods / 16. Quality homes / 17. Rural homes / 18. Infrastructure first / 19. Heat and cooling / 20.Blue and green infrastructure / 21.Play, recreation and sport / 22.Flood risk and water / management / 23.Health and Safety / 24.Digital infrastructure	A Connected Scotland / A Healthier Future: Scotland’s diet and healthy weight delivery plan / Cleaner Air for Scotland 2 / Creating Places / Culture Strategy / Heat in Buildings Strategy Housing to 2040 / Learning Estate Strategy/Learning Estate Investment Programme / Public Health Priorities for Scotland / Remote, Rural and Islands Housing Action / Scotland’s Population Strategy	Local Housing Strategy / Food Strategy / Air Quality Strategy (under preparation)

Productive Places
NPF4 Policies	Key Scottish Government links	Council Plans/Strategies
25. Community wealth building / 26. Business and industry / 27. City, town, local and commercial centres / 28. Retail / 29. Rural development / 30. Tourism / 31. Culture and creativity / 32. Aquaculture / 33. Minerals	National Strategy for Economic Transformation / Retail Strategy for Scotland / Report of the City Centre Recovery Taskforce / Scottish land rights and responsibilities statement / Town Centre Action Plan 2	Economic Strategy / Community Wealth Building Strategy / Social Enterprise Strategy / Tourism Strategy / Various town centre strategies

## Annex 2 Matters to be addressed in the LDP3 Evidence Report
- The principal physical, cultural, economic, social, built heritage and environmental characteristics of the district;
- The principal purposes for which the land is used;
- The size, composition, health and distribution of the population of the district;
- The housing needs of the population of the area, including the needs of persons undertaking further and higher education, older people, disabled people;
- The availability of land in the district for housing, including for older people and disabled people;
- The desirability of allocating land for the purposes of resettlement;
- The health needs of the population of the district and the likely effects of development and use of land on those health needs;
- The education needs of the population of the district and the likely effects of development and use of land on those education needs;
- The extent to which there are rural areas within the district in relation to which there has been a substantial decline in population;
- The capacity of education services in the district;
- The desirability of maintaining an appropriate number and range of cultural venues and facilities (including in particular, but not limited to, live music venues) in the district;
- The infrastructure of the district (including communications, transport and drainage systems, systems for the supply of water and energy, and health care and education facilities); [the reference to energy includes land available for the development and use of facilities for renewable sources of energy.
- How that infrastructure is used; and
- Any change which the planning authority thinks may occur in relation to any of the matters mentioned above.

The Evidence Report must also set out the following:
- A summary of the action taken by the planning authority to support and promote the construction and adaptation of housing to meet the housing needs of older people and disabled people in the authority's area, and analysis of the extent to which the action has helped to meet those needs.
- A summary of the action taken by the planning authority to meet the accommodation needs of Gypsy/Travellers in the authority’s area, and an analysis of the extent to which that action has helped to meet those needs.
- How the authority has invited local communities to prepare LPPs, and what assistance they have provided.

## Annex 3 Additional Assessments

 Other impact assessments are required to be carried out alongside the plan preparation process. The assessments include:

Strategic Environmental Assessment	This is a statutory requirement to ensure the environment is a primary consideration when preparing the plan and that the environmental and sustainability implications of the emerging plan and its proposals are assessed. It allows a better understanding of the environmental context and sets out the steps to avoid, mitigate or reduce significant adverse impacts, or indeed enhance any positive ones. SEA will be based on the council’s State of the Environment report. A link to 2021 version is here, South Lanarkshire State of the Environment Report 2021, however it is expected that the updated 2023 version will be available during the Evidence Report stage. Scoping of the Evidence Report will be done in tandem with the scoping report for the SEA.
Habitats Regulations Assessment	This is a statutory requirement to consider the potential impacts of the proposed plan on internationally important wildlife sites. The HRA will be done as we consider the ideas presented to us during the preparation of the proposed plan as well as any sites carried forward from LDP2. Any policy content in LDP3 will also be subject to HRA assessment.
Equalities Impact Assessment	This ensures that a wide range of people are involved in shaping their places during the plan making process. The Participation Statement is a key document in this regard. In addition, the UN Convention on the Rights of the Child means young people are actively encouraged to play a part. We will ensure children and young people are fully and appropriately engaged as described in the Participation Statement.
Public Sector Equality Duty	This is intended to ensure the council seeks to eliminate discrimination, advance equality of opportunity and foster good relations between persons who share a protected characteristic.
Fairer Scotland Duty Assessment	This places a legal responsibility on the council to consider how they can reduce inequalities of outcome caused by socio-economic disadvantage when making strategic decisions so that we make better policy decisions and deliver fairer outcomes. Key issues include low income, low wealth and area deprivation. It will be important to engage with relevant communities to understand the issues faced.
Health Impact Assessment	Health impact assessment (HIA) considers the potential, and sometimes unintended, effects a policy, strategy or service plan may have on the health of a population. It is particularly useful for considering effects on vulnerable or disadvantaged groups. HIA considers the socioeconomic determinants of health and how they influence health outcomes. Evidence from research, data and the experience of stakeholders is used to inform the assessment.

## Annex 4 Engagement Strategy

### A. Programme

1	Internal information gathering and preparation January to April 2024

1.1	Gather information from other departments and Community Planning Partners:
- Their existing networks and ongoing engagement activities (see Appendix for a list of key networks) – see section A overleaf.
- Results from recent consultations and engagements across South Lanarkshire (which might have been led by the council, Community Planning Partners or local communities).
- Existing plans, policies and strategies in South Lanarkshire (potentially led by the Scottish Government, council, Community Planning Partners or local communities; could be national, regional, local authority wide or more local) – see section A overleaf.
- ‘Hard’ facts and statistics (population, housing, nature, contamination, transport, education).
- Understanding of parameters that have to be delivered – NPF4, capital programme.

1.2	Prepare community engagement plan:
- Cover how, where and when to engage.
- Use existing structures like Citizens Panel and community groups to test how best to engage.

2	Initial community engagement May to September 2024

2.1	Aims:
- Ask about people’s lived experience of their place / their community – what’s good, what’s bad, what ideas they have for the future.
- Sense check what we understand about communities / places from existing data and information gathered in stage 1.

2.2	Key principles (see sections C-E overleaf for more details):
- Use simple, standardised open questions.
- Presentation and style are critical to maximise response – simple, non-judgmental.
- Use opportunities to drill down into more place-specific detail where appropriate (in discussion events) – remembering that ‘drilling down’ discussions can continue after the evidence report has been submitted to the gate check.
- Understand that people’s responses will relate to land-use planning and other public services – so outputs should be shared across other services.
- Provide feedback to participants about how their inputs are being taken forward (for LDP3 and other public services) and to keep them updated on the process.

3	Share Evidence Report with communities Spring 2025

3.1	Once submitted to the Scottish Government DPEA, share the gate check report to those who have participated and the wider public, noting that it combines:
- Hard ‘quantitative’ data about places and ‘qualitative’ data about people’s lived experience and aspirations.
- Parameters and requirements that LDP3 must abide by (NPF4 policies).
- Areas of dispute.

3.2	Use the gate check report as the basis for developing community engagement strategy and plan for next phase of community engagement – to develop LDP3 itself.

### B. Tapping into what already exists

B1: Established networks:
- Citizens’ Panel – could use to ask about how best to engage the wider community, as well as engage about the plan itself.
- Schools and education – climate forum, school lessons / curriculum.
- Social Work Champions’ Board – care experienced young people.
- Youth work - Universal Connections (“Inclusion is Prevention”).
- Local community classes, teachers, organisers and instructors – they know people already.
- Age Friendly South Lanarkshire, Seniors Together Group.
- Community police.
- Locality Planning Group members – health prevention teams.
- Streetscape employees.
- Federation of Small Businesses / SLC Economic Development – networks and use Town Centre Action Plans as source of business views.
- Community Partnerships and Locality Planning Groups.
- Other third sector / community organisations.
- Gypsy travelers – working relationship already exists.
- Other existing networks listed in the Appendix. See also organisations listed under E2 below and in the Appendix.
B2: Existing information about places and communities:
- 30-40 communities across South Lanarkshire already have worked up ideas of what they want – that will give an understanding of their community-led planning priorities.
- Community Planning activity.
- Place and Wellbeing Assessments and Recommendation (Shaping Places for Wellbeing).
- Key council strategies / priorities.
- Experian/Acorn data.

### C. Information to gather and questions to ask

C1: Questions to uncover people’s lived experience of their community and place – so planners can get to know and understand communities on their terms:
- Open questions – What do communities want? What do you like and not like?
- Look to identify local assets and opportunities, as well as problems and challenges – what’s unique about your community?
- What would make a difference to your community?
- Look for opportunities where communities can deliver things (and the public sector maybe cannot) – the LDP needs to be the community’s document as well as the council’s.
- Young people – what’s your next step? Why?
- What do you think of SLC?
- Have information available about contacts in other council departments.

C2: Share and sense check existing information and stats about communities (down to datazone / intermediate zone levels) - to prompt discussions about people’s lived experience, and to sense check / critique:
- SIMD – equalities info, child poverty, fuel poverty
- Demographics – population change, projections, age distribution
- Economy – disposable income, employment.
- Health
- Amenities – access and quality (‘Local Living’ features)
- Transport
- Housing – need/demand, waiting list info, housing condition reports, where to people want to live, empty homes, council tax bands
- Land use audits: vacancy and dereliction, industry, commercial, retail, land ownership
- State of Environment report – climate change, nature, biodiversity, flooding, contamination.
- Rural

### D. Who we need to engage with

D1: We need to reach a range of people:
- Under-represented groups who don’t normally engage (“hard to reach” / “seldom heard” voices).
- Children and young people
- Older people
- Women and girls
- Disabled people
- LGBT
- People with learning difficulties / neuro diversity
- Vulnerable people (“protected characteristics”)
- Carers
- Businesses large and small
- Farmers
- Third sector organisations / social enterprises

D2: Geographical focuses:
- People in deprived communities / SIMD areas – unemployment, income deprivation, learned experience (from living through problems, dealing with people with addictions, care experience).
- Communities we don’t hear from – “the Glespins”.
- Range of settlements of different sizes – including small rural villages / clusters.
- Green spaces / parks.
- Town centre users – East Kilbride, Hamilton and Lanark (crime, safety, feelings).
- Tourist sites.

D3: Outwith South Lanarkshire:
Rural and urban cross boundary: Glasgow city region, West Lothian, Scottish Borders, Dumfries and Galloways, the Ayrshires

### E. How we need to engage

E1: Approaches / principles:
- Balance quantitative data/hard facts and qualitative data/stories/lived experience. Share hard data to encourage different perspectives and to sensecheck (see C2 above). But avoid “info bombing” people with too much data – it’s their lived experience we’re looking for.
- Range of methods, activities and channels
- Reflect and adapt as we go along.
- Make sue materials are simple and graphic.
- Engage through existing networks (see B1 above, E2 below, and Appendix).
- Targeted engagement led by specialist officers.
- Tailor engagement to audience/participants – example, those not online.
- Let people choose how to engage – need a choice of different approaches.
- Go where people are. Be proactive and seek people out. Join community events, visit and get to know/understand communities.
- Use open questions to start with: ask communities what they want (see C1 above).
- Make it human – encourage personal stories, share “a genuine warm smile”
- Language and tone are important – “don’t give it the NPF4”
- Honesty is critical – be honest about what can be achieved in response to people’s aspirations. Know what our parameters are before we start (NPF4, capital programme).
- Tools – digital is important (to promote engagement and enable online response on phones and tablets), ipads, Ketso toolkit, opinion matters mapping, digital storymap. (but all need resourcing).
- Feedback good news stories – to demonstrate that it’s worth getting involved.
- Gather contact information to enable feedback and to share with other services (to enable response to non-planning suggestions which are passed to other services) – and have contact information available about other council departments.
- Demographic profiling – who to reach.
- Targeted focus groups for deeper dive discussions (could happen after submission of evidence report too, to help develop the LDP itself).

E2: People, groups and organisations we can use as ‘ways in’ – those listed in B1 above and the Appendix, plus:
- Community champions, community representatives, community activists
- Environment: Beeline to Nature / Langloch Farm, Outlet Resource (forest education for children / young teens)
- Health: Community Connectors in GP surgeries, NHS Lanarkshire, public health services, The Beacons (alcohol/drug rehab), crime prevention partners based on Safer South Lanarkshire, events based on themes
- Sports and physical activity: football teams (example, Accies and junior teams), racecourse, basketball team in East Kilbride, walking, rambling, horse riding, cycling groups/clubs, fitness classes/instructors (Patrick Murphy at SLLC)
- Faith: example Church of Scotland (closures), Churches Together (all faiths)
- Education – UWS, S Lanarkshire College, Parent councils (Des Dickson in Education), pre-school
- Business – BIDS (Lanark, Hamilton, possibly Carluke), social enterprise strategy (Yvonne McBride)
- Lanarkshire Carers
- Refugees
- Young Scots
- Men’s and Women’s Sheds
- Developer forum
- Tenants / Residents Associations
- VASLAN
- Landlords
- Veterans’ groups

### F: List of existing networks

Name of network	Localities covered	Membership/attendees	Purpose
Local Housing Forums	All / There are 8 forums covering the following areas: / -Cambuslang / -Rutherglen / -Blantyre / -East Kilbride / -Hamilton / -Larkhall / -Lanark / -Carluke	-Tenants and residents / -SLC / -Third sector, public and private sector organisations can be invited along	The forums meet regularly to consider a wide range of important matters including progress in relation to the HomeHappening improvement programme, local performance information and issues such as the allocations policy, repairs, rent setting and of course, tenant participation. / Meetings are open to all tenants and residents. Senior officers from the local housing office and local area councillors also attend. If tenants want to discuss specific issues in relation to other council or public services, guest speakers from other council departments as well as organisations such as the police can be invited to attend the forum.
Local Licensing Forums	1 in each locality.	Membership is made up of representatives from key areas in the community:- / -Holders of premises licences and personal licensee(s) / -The chief constable for the area / -People working in Health, Education or Social Work / -Young people / -People who live in the area / At least one of the members must be a Licensing Standards Officer.	The forum's role is to review the licensing board's decisions and consider what these will mean for the community. / The forum may give advice and make recommendations to the licensing board. The objectives are to:- / -prevent crime and disorder / -secure public safety / -prevent public nuisance / -protect and improve public health / -protect children from harm
Health and Social Care Forums	1 in each locality.	The forums are made up of members of the public, carers, local community groups and voluntary organisations. You do not need to be a member of an existing group to join.	Roles include: / -Informing local people about the range and location of services and information for which the health and social care partnerships are responsible. / -Involving local users of service, carers and the public in discussion about how to improve local services. / -Support wider public involvement in planning and decision-making about services that are delivered locally. / The forums feed into the locality implementation groups.
Local Action Planning Groups	1 in each locality.	Membership currently includes Community Planning, Education (Youth Family and Community Learning Service (Youth Work, Adult Learning, ESOL) and Senior Management Pupil Support), NHS Lanarkshire, South Lanarkshire College, UWS, VASLan, Healthy Valleys, Clydesdale Community Initiatives (CCI), Skills Development Scotland, and South Lanarkshire Leisure and Culture. Membership is being considered to ensure that widest engagement with partners exists.	Each of these locality networks are made up of statutory, public and voluntary sector organisations who are key in both planning and delivery of opportunities and services under the Community Learning and Development 3-Year Strategic Plan, seeking to ensure no duplication of effort or resources, identify gaps in provisions and seek opportunities to progress these for the betterment of the communities that the groups serve. They meet quarterly and currently seeking to ensure that the dates do not clash with other forums such as the Third Sector Forum for instance.
HSCP Locality Implementation Groups	1 in each locality.	Each of the Locality Implementation Groups consist of a range of partners working closely across each of the localities including carer representation, third sector, independent sector, Health and Social Partnership, South Lanarkshire council, NHS Lanarkshire, Police Scotland and Scottish Fire and Rescue.	The groups have responsibility for ensuring better integrated working benefits communities, local residents and informs service redesign and improvement. The Locality Implementation Groups provide the infrastructure to support collaborative engagement of all stakeholders in the community and implementing the Strategic Commissioning Plan. / This groups will help to support and empower the people of each of the localities in South Lanarkshire to identify and deliver their priorities, ensuring that this feeds into the wider Commissioning Planning process.
Third Sector Locality Networks	1 in each locality.	Anyone working with organisations or community groups in South Lanarkshire is welcome to come along to the Third Sector Locality Networks.	Following an application process open to all South Lanarkshire third-sector organisations, the new Third Sector Locality Networks were launched in September 2022 under the leadership of locality-based partnerships. / The new events replace the previous Third Sector Forum (TSF) structure, with the ambition of forming a distinct, sector-led network in each of South Lanarkshire’s four localities to better showcase the depth of the sector, share best practices, access peer support and identify locality specific challenges, as well as opportunities for collaborative working. The events are held quarterly on a March, June, September and December cycle. / The locality-based partnerships, with the lead facilitators for the events, are as follows: / Clydesdale: Clydesdale Community Initiatives (CCI) and Healthy Valleys. / East Kilbride and Strathaven: Connected East Kilbride (Kilbryde Hospice, Healthy and Active in East Kilbride and East Kilbride Citizens Advice Bureau). / Hamilton, Larkhall and Blantyre: The David Livingstone Trust and Lanarkshire Association for Mental Health (LAMH). / As there is no locality-based partnership in place for CamGlen as of yet, VASLan currently facilitate events in this locality.
South Lanarkshire Social Enterprise Network (SLSEN)	South Lanarkshire wide	Anyone involved with social enterprises both on a local scale and with national organisations which are a part of the Social Enterprise Ecosystem.	The South Lanarkshire Social Enterprise Network (SLSEN) is a membership network of South Lanarkshire social enterprises that believe social enterprise can transform the economic, environmental, social, and cultural life of South Lanarkshire. By supporting, promoting and developing social enterprise, the SLSEN aims to create an environment in South Lanarkshire in which social enterprises are able to flourish. Meetings are held approximately every six weeks and hosted at a different social enterprise and locality on each occasion.
Employability Network	South Lanarkshire wide	All third sector organisations in South Lanarkshire who support individuals on their employability journey from assessment to in-work support, including tackling barriers to employment.	The Employability Network is a network of third sector organisations and partners with a shared interest of advancing employability in South Lanarkshire. Launched in July 2023, the network is currently developing and hopes to provide capacity building, training and support to third sector organisations across South Lanarkshire who are assisting people on their employability journey.