# Annual Governance Statement 2023-24 – Significant Governance Areas

 Quarter 4 update – September/October 2023 to March 2024

Areas identified in 2023/2024	Actions	Quarter 4 Progress
1. Cyber Resilience / Compliance with legislative and regulatory policy	A programme of actions to maintain cyber security and resilience in 2023/2024 will include: / Refresh/retiral of legacy systems, network equipment and end user devices (mobile phones, PCs) / Programme of security patching of all systems / Compliance with PSN and Cyber Essentials schemes / Incident response / Officer training and awareness (for example phishing) / Data security reviews as part of new system installation / Security monitoring	Refresh programme is ongoing, retiral of legacy systems is monitored and reported on by the IT Security team on a fortnightly basis. / Monthly and Quartey patching are scheduled tasks across the estate. / SLC aligned to PSN and Cyber Essentials Plus standards. / Incident response is reviewed by the IT management team working with the Resilience team. / Ongoing awareness driven by regular campaigns such as Cyber Scotland week and posts to the Intranet. / Security reviews are embedded into the onboarding of new systems.

Areas identified in 2023/2024	Actions	Quarter 4 Progress
2. Financial Challenges / Exceptional increase in costs, reduction in council funding, resulting in difficulties maintaining front line services.	The council faces a challenging situation in the medium to long-term because of reduced funding in real terms, rising costs and an increase in demand. In addition, there are exceptional increases in costs being experienced resulting in significant budget gaps that will require to be managed. / The council has developed a long-term strategy which identifies budget pressures, future risks and uncertainties, and projects budget gaps to 2028/2029.	The Budget Strategy for 2024/2025 was updated and presented to the Executive Committee in June 2023 and a Budget Sounding Board and latterly a Budget Working Group with cross party membership was formed to allow advance preparations for the council Budget Setting in 2024/2025. Regular updates were provided to Members throughout 2023 and early 2024 and the Budget was set in February 2024. / Work has commenced on the 2025/2026 to 2027/2028 Budget Strategy with a report to be presented to the Executive Committee in June 2024. / Support for tenants in financial hardship has been identified via Tenancy Sustainment Fund to assist them to pay their rent. The rent setting survey for 2024/2025 took place early in the year, with tenants being given opportunity to attend local focus groups. The output of the consultation fed into the rent setting and budget which was set in February 2024.

Areas identified in 2023/2024	Actions	Quarter 4 Progress
3. Integration Joint Board – Health and Social Care / The need for the council to deliver the objectives set out in the Integration Joint Board (IJB) Strategic Commissioning Plan 2022 to 2025	The current strategic direction set out and approved by the IJB is detailed within the Strategic Commissioning Plan. The council and NHS Board are required to deploy their resources in line with this strategic direction. / The IJB issues Directions that set out the key actions to be delivered by the council during the year 2022/2023 and these Directions were agreed by the IJB at it special budget meeting in March 2022. / The council will provide progress updates against Directions for which it is the lead organisation.	The IJB adopted the Sustainability and Value Options Appraisal programme in September 2023 to support its delivery of a balanced budget for 2024-2025, in line with its statutory duties. Proposed savings options across health and social care services were presented to the IJB for approval on 26 March 2024. / An update was provided on the Integration Scheme Review at the IJB meeting on 26 March 2024. It included / proposed changes to the Directions and notification that Scottish Ministers had approved the revised integration scheme approved by South Lanarkshire Council and NHS Lanarkshire. / The Annual Performance Report (APR) was published for 2022/2023 providing an overall assessment of performance in relation to the statutory/governance requirements related to performance and progress on the priorities outlined in the Strategic Commissioning Plan 2022 to 2025 (SCP). The APR for 2023-2024 is in progress. / A Progress Report on the Internal Audit Plan 2023-2024 was presented to the IJB at a meeting on 20 February 2024. A workplan was agreed to deliver the 2023/2024 Internal Audit Plan by 31 March 2024. The Internal Audit Plan 2024/2025 was submitted at the IJB meeting on 20 February 2024.
4. Review of Community Planning / Provide support to the review of Community Planning arrangements	During 2019, the Community Planning Partnership Board undertook a self-assessment of the current Community Planning arrangements. Improvement actions were later supplemented by the recommendations from the council’s Best Value Assurance Review and a group was set up to take these forwards. / The review focuses on several key areas including structures, governance, and accountability arrangements. The council will provide resources to support the implementation of the agreed actions. / The proposal was approved by the Community Planning Partnership Board at their meeting in September 2020. This highlighted a two-phase approach to implementation, with interim actions to be delivered during the 2021/2022 year leading to final improvements, particularly around structures, during 2022/2023 in order to ensure that the partnership is fit for purpose to deliver the outcomes within the new Community Plan, which will be created using a co-production model during 2021/2022. / Interim structures are in place and the new Community Plan was presented to the CPP Board for approval on 22 June 2022 together with a progress update on structure changes. Further progress updates were made to the CPP Board on 14 September 2022 detailing the changes required to governance structures in order to deliver the plan. Work continues with the partners to progress changes.	Following a full review of Community Planning structures and plans, on 22 March 2023 the Community Planning Partnership Board approved a new Thematic Board structure. On 6 September 2023, the Board approved its revised Governance Framework. The final part of the review is to develop a proposal for partnership working at a locality level. Work continues with the Outcomes Leads Group to deliver on this.
5. Community Wealth Building / Deliver the Community Wealth Building Strategy	The Community Wealth Building Strategy which was approved in March 2021 will bring fundamental changes to how the council delivers its services and works with its partners and communities. In August 2021 the Community Wealth Building Commission approved an action plan containing a range of actions to progress the aspirations of the Strategy over a 3-to-5-year timeframe. A risk register has been developed and approved. Risk monitoring arrangements are in place. / An annual report highlighting progress over the first year of the Strategy was presented to the Commission on 28 June 2022 for approval.	The work building on the CWB Strategy continued throughout 2023-24. The Q4 update on the 2022/2023 Action Plan was approved by the Commission on 6 June 2023. The Action Plan was then given a refresh, following an annual review led by FCR with input from other Resources, which was approved on 5 September 2023. The 72 actions will be progressed throughout the year and will be reported on at Q2 and Q4. In addition, the Commission agreed on 7 February 2022 that CWB annual reports should be produced to bring the work to a wider, public audience. The most recent of these was approved on 5 September 2023. Risk monitoring remains in place and the CWB risk register is presented annually. / A review of the Community Wealth Building Risk Register is underway. The outcome of the review will be reported to the CWB Commission later this year.
6. Sustainable Development and Climate Change	The council acknowledges the serious and immediate threat of climate change and is committed to accelerating the pace of action in response to the climate emergency and in Scotland’s transition to a net-zero and climate resilient society and economy. A review of the council’s Sustainable Development and Climate Change Strategy (2017-2022) has commenced and is scheduled to conclude during 2022; and a new Strategy for 2022-2027 was developed and presented to Council in June 2022 for approval together with the council Plan and Community Plan. An Action Plan is being developed covering the 5-year period of the Strategy. The Action Plan will be reviewed annually with progress updates being reported to the Climate Change and Sustainability Committee on a 6 monthly basis.	The council’s Sustainable Development and Climate Change (SDCC) Strategy 2022 to 2027 and its accompanying 5-year action plan was developed in 2022. / Delivery of the SDCC action plan provides the main focus for SLC’s sustainable development activity. The first year of this action plan was implemented with progress against the actions monitored using IMPROVe and reported to the Climate Change and Sustainability Committee at quarter two (28 February 2024) and quarter four (due for presentation 14 August 2024). / The action plan for the second year of the strategy has now been developed and will be presented to the Climate Change and Sustainability Committee on 14 August 2024. As above, progress updates on implementation of this new plan will be reported to the Climate Change and Sustainability Committee on a 6 monthly basis. / Development of full Local Heat and Energy Efficiency Strategies (LHEES) continues. A consultation was undertaken between February – April and a report on progress was presented at the Sustainable Development and Climate Change committee in February 2024. The draft LHEES strategy will be reported to the Corporate Management Team in May. Following this, the Strategy will be reported to the Executive Committee for approval on 26 June 2024. / The council is also committed to raising awareness and empowering young people to become active participants in work around climate change and sustainability. The recent Pupil Climate Conference (COS2 - Conference of Schools) highlights the ongoing commitment to this. The council now needs to continue to establish sustainability throughout more than just the life and ethos of our schools, but as part of a refreshed curriculum offer, in which learners regularly learn about sustainable issues and share depth of learning with the wider school community.
7. Economic Strategy	The new draft Economic Strategy 2022-2027 has been developed and approved by Council on 15 June 2022 as part of a suite of documents accompanying the draft Council Plan and Community Plan. The vision within the Strategy is “to make South Lanarkshire a flourishing, green, dynamic and equitable place for communities, visitors, businesses and investors”. The Strategy is framed around the 3 themes of sustainable, inclusive, economic development- People, Place and Business. / Further online consultation on the Strategy took place during July and August. Progress on the delivery of the Action Plan will be measured 6-monthly with the results being reported annually to the relevant committees. / The council will continue to lead on local economic recovery for South Lanarkshire businesses through promotion of local economic support networks and contribution to the pan-Lanarkshire Economic Forum.	The annual update on the Economic Strategy was presented to the Community and Enterprise Resources Committee on 23 April 2024. The committee noted the progress in the last year since the strategy was approved by Committee and the updates to the action plan. / The initial year of the strategy was used as an opportunity to reassess and reset the benchmark as the economy recovers and the impacts of COVID-19 are addressed. / Further update reports will be taken to committee to keep members informed of progress against the strategy and action plan.
8. Recruitment and Retention Challenges	COVID-19 and Brexit have had a substantial impact on recruitment and retention as the labour market has tightened and employees have more mobility through agile working which is not necessarily tied to a geographical location. In addition, some older workers have reassessed priorities and taken up an option for partial or full retiral earlier than they would have done previously. / As a result, there are a number of skills in short supply nationally and this is putting pressure on local government services. Examples of this include HGV drivers, procurement and Social Care. The impact on Senior Manager recruitment and retention is also clear and turnover at this level is closely monitored / South Lanarkshire Council has experienced these issues and is taking the following actions: - / Workforce Plans were refreshed to reflect the changed environment by 30 June 2022. The updated plans were reported to the relevant Resource Committees in September and October 2022. / A grow your own approach is being used in key areas (recruited graduates in Procurement) / Increasing social media recruitment and use of job fairs / Employability routes are being defined for skills shortage areas (for example social care) / Enhanced employee support arrangements are in place but also being reviewed for development	Recruitment and staff retention has been challenging for Social Work Resources in recent years and workforce availability remains in the top five risks on the Social Work Risk Register. Workforce supply availability is also a notable risk for partners and commissioned services, and this creates an inherent risk for the Resource. / The Locality Based Social Work Services’ Modernisation Programme identified the need to update the model of service delivery across localities to meet growing demand on statutory duties relating to assessment and care management, mental health and public protection. Proposed changes to the staffing establishment were approved by Social Work Resources Committee on 28 June 2023 and demonstrated a commitment to the recruitment and retention of the workforce by enhancing career pathways and succession planning for existing staff. / Workforce is included in the Education Resources risk register for 2023/2024. / The Education Resources workforce plan for 2022 to 2025 was endorsed by the Education Resources Committee on 6 September 2023. / In the annual census Education Resources complied with and met the target for teacher numbers in September 2023. / However, recruitment in other areas may slow due to the unprecedented financial pressures facing the council. / Community and Enterprise Resources have deployed revised recruitment practices to address challenges, examples include: / rebranding adverts within facilities including information on how to maximise income for those on benefits. / Roadshow to attract candidates for mechanics and drivers; and / Targeted recruitment for planning officers, including trainees and graduate appointments. / Within Housing and Technical Resources, the council has redesigned job roles, used targeted recruitment (surveyors). The Modern Apprentice programme within Housing continues to attract high numbers of candidates and is very successful in ‘growing our own’ talent. / Within Finance and Corporate there has been changes to criteria for some posts across finance to attract a wider pool of candidates. The Resource continues to utilise employability routes and supports recruitment fairs.

If you need this information in another language or format, please contact us to discuss how we can best meet your needs. Phone 0303 123 1015 or email equalities@southlanarkshire.gov.uk